## Risk_Database xlsx
ver | proj_id | proj_name | sgmnt | state | risk_code | risk_name | risk_desc | Level1
Initial |  | Goethals Bridge Replacement |  | NY |  | Labor or material shortage | Labor resources become unavailable. Material specified by PA in design becomes unavailable or commercially unreasonable to procure | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Early start of construction | The Developer starts construction before PA has reviewed all necessary design deliverables. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Unsafe Working Practices | The Developer seen to be conducting unsafe working practices. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Failure to Report Known Defect | Failure by the Developer to report and act on a known defect. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Failure to perform qualtiy assurance and quality control | Failure by the Developer to follow a requirement of an approved management plan, e.g. failure to perform QA/QC diligently and at required levels | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Construction Oversight by owner | Owner unable to undertake oversight of critical activities (denial of access, insufficient staff availability) | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Worker Health and safety | Worker health and safety policies and procedures are not properly developed, communicated, updated, implemented and/or monitored. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Traffic management | Traffic management during construction is unsafe and/or inefficient | Traffic
Initial |  | Goethals Bridge Replacement |  | NY |  | Construction Environmental noise constraints | The Developer fails to meet environmental constraints e.g. no in-water work between January and June. Construction noise and dust constraints. [This would reflect badly on PA if environmental requirements breached]. | Environmental
Initial |  | Goethals Bridge Replacement |  | NY |  | Diffential and ground settlement | Excessive or differential settlements of neighboring assets caused by additional loads from new bridge construction | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Working Hours | Onerous working hours | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Political and union impacts on construction | Third party challenges (ie, US Steel Manufacturers, Unions, etc.) could lead to schedule delay, political settlement, cost) | Management and Funding
Initial |  | Goethals Bridge Replacement |  | NY |  | Ongoing Involvement of Owner Staff | Loss of Key Owner Personnel could result in delay (approvals, etc). Unclear PA organization could result in design and construction delay. Delays in invoice processing/payments. | Organizational
Initial |  | Goethals Bridge Replacement |  | NY |  | Construction Incidents | Construction Incidents and accidents that impact owner and/or third party. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Extreme Events | Extreme Events (Seismic or wind) delay construction | Management and Funding
Initial |  | Goethals Bridge Replacement |  | NY |  | Substantial completion | Dispute over whether substantial completion has been reached and/or C. of O. can be issued. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Quality of Steel or concrete is sub-standard | Quality of Steel Fabrication and/or concrete is sub-standard and rework is required | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Stakeholders Operational restrictions/ coordination resulting in restaging or restrictive work windows. | Operational restrictions (e.g. NJ Turnpike restricted work hours) or coordination issues resulting in restaging or restrictive work windows. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Contractor proposal to incorporate new technology | Contractor proposes to use new technology that requires PA to evaluate possibly delaying construction activity. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Problem with bridge assembly over AK results in cessation of shipping | Bridge assembly over Arthur Kill has problems which result in a cessation of shipping. | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Incident Management | [User incident on new bridge results in temporary facility or lane shut-down.] User Incident on new Bridge results over operating period in longer periods of facility or lane closure than originally planned | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Vehicle accident on bridge (or ships/boats below) and damage to asset | Collision or vehicle fire causes damage to bridge structures | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Hazardous Cargo | Incident involving hazardous cargo during operating period gives rise to a recognized Environmental condition | Environmental
Initial |  | Goethals Bridge Replacement |  | NY |  | Drainage Treatment | Failure of bridge drainage treatment system in operation causes pollution incident. [May result in adverse consequence to PA e.g. adverse publicity] | Environmental
Initial |  | Goethals Bridge Replacement |  | NY |  | User incident rate | User incident rate during operation of bridge exceeds specified limits | Construction
Initial |  | Goethals Bridge Replacement |  | NY |  | Managed Use Lanes | PA requires additional enforcement characteristics, e.g. in-lane occupancy detection system or physical barrier constraints | Traffic
Initial |  | Goethals Bridge Replacement |  | NY |  | Transfer of Owner Labor | Transfer of owener labor due to handover of bridge to developer could lead to owner cost in transferring or redefining the labor requirements. Defining emergency response roles could lead to impact of labor harmony, political issues and duplicative costs. | Organizational
Initial |  | Goethals Bridge Replacement |  | NY |  | Police Closure on Bridge | Police close bridge or lanes without discussion with developer. | Traffic
Initial |  | Goethals Bridge Replacement |  | NY |  | Changes to Structural Elements Design Required | Owner carries out security review/upgrade on bridge and determines that changes to structural design elements are required. | Design
Initial |  | Goethals Bridge Replacement |  | NY |  | The Developer lack of resources to properly oversee O&M requirements | The Developer lack of resources available to properly oversee the O&M requirements. Could lead to overpayment or non-compliance by vendor with contract requirements. | Organizational
Initial |  | Goethals Bridge Replacement |  | NY |  | Terrorist attack on Bridge | Terrorist attack on bridge results in catastrophic event after new bridge is put into commission | Management and Funding
Initial |  | Doyle Drive/Presidio Parkway Project (Phase II) |  | CA |  | The pursing of SPUR of the "half circle" Drive design concept to the eastern end of the proposed Doyle Dr | The risk involved here that this design has been proven to be faulty and may cause a high rate of accidence. Also potential reaction of tenants living along Richardson Ave. | Design
Initial |  | Doyle Drive/Presidio Parkway Project (Phase II) |  | CA |  | The "Purpose and Need" statement inclusion of the Access concept to Doyle Drive design | The lack of Alt. 2 to the Access to the Presidio provide a bigger risk of the PT rejection to that alternative at the end of circulation. | Design
Initial |  | Doyle Drive/Presidio Parkway Project (Phase II) |  | CA |  | The request from Golden Gate Bridge District (GGBD) to add a Merchant Ramp design to Doyle Dr | This Design option can have an impact on cost if selected in the public circulation | Design
Initial |  | Doyle Drive/Presidio Parkway Project (Phase II) |  | CA |  | The intended submittal list of the "Design Exceptions" for Alternative "5" and potential taking it for granted | This is a potential risk as Alt. 5 is favored with all its' elements of Design to the other agencies and any possible rejection of an exception could trigger a delay in schedule | Design
Initial |  | Doyle Drive/Presidio Parkway Project (Phase II) |  | CA |  | Amongst all the Design Exception the "Inside" shoulder exception and the potential justification. | This sounds to be the most problamatic among all of the design exceptions and could trigger a major delay in the schedule | Design
Initial |  | I-70 East |  | CO |  | Utility Phasing | As a result of Utility conflicts during construction would lead to schedule delays and cost | Utilities
Initial |  | I-70 East |  | CO |  | Utility agreements prior to final request for proposal | If utility agreement process is time consuming would lead to schedule delays; delay cost | Utilities
Initial |  | I-70 East |  | CO |  | Seasonal restrictions on utilities during construction | As a result of seasonal impacts to utility relocation would lead to schedule delays; delay cost | Utilities
Initial |  | I-70 East |  | CO |  | Utility railroad agreements / schedule / costs | As a result of Non-cooperation of utility company; impact to RR property and operations would lead to potential delay of final RFP, added cost for contractors | Utilities
Initial |  | I-70 East |  | CO |  | Relocate utility shared resources | As a result of relocate I-70 fiber backbone would lead to increased cost | Utilities
Initial |  | I-70 East |  | CO |  | Timely railroad collaboration ( RailRoad undertaking own construction scope) | As a result of railroad wants to do some trackwork themselves would lead to construction delays | Stakeholder
Initial |  | I-70 East |  | CO |  | Failure to get agreement with stakeholder | As a result of stakeholder policy and agreement would lead to impact Design schedule | Stakeholder
Initial |  | I-70 East |  | CO |  | Local agencies causes additional analysis that impacts schedule | As a result of Local agency request through procurement/construction would lead to increased costs and schedule delays | Stakeholder
Initial |  | I-70 East |  | CO |  | Getting agreement with stakeholder | As a result of storm sewer crossing, getting agreement with stakeholder, would lead to schedule delay/cost | Stakeholder
Initial |  | I-70 East |  | CO |  | Constructability of bridge | As a result of tight construction site; deep construction; unknown requirements the constructability issue | Design
Initial |  | I-70 East |  | CO |  | Change management | As a result of 3rd party late change requests, errors in contract documents, or unforeseen events would lead to schedule delays and additional cost | Stakeholder
Initial |  | I-70 East |  | CO |  | Design change | As a result of inability to come to resolution with CCD and DPS on design elements for cover would lead to design change and additional costs and schedule delays | Design
Initial |  | I-70 East |  | CO |  | Changes in codes and standards during project | Due to duration of the project would lead to potential change order during construction | Management and Funding
Initial |  | I-70 East |  | CO |  | Structure selection depth - utility integration conflicts | As a result of utilities being attached to structures at specific locations would lead to reduced overhead clearance for I-70 | Utilities
Initial |  | I-70 East |  | CO |  | Aesthetics requirements | As a result of changing or undefined aesthetic scope would lead to additional costs and schedule delays | Design
Initial |  | I-70 East |  | CO |  | Economic change and Accuracy of current cost estimates | As a result of market pricing variations and scope changes would lead to proposals are over MPP Upset Limit | Management and Funding
Initial |  | I-70 East |  | CO |  | Ineffective and unenforceable Quality Asurrance and Quality Control practices | As a result of developer not managing the Quality Asurrance and Quality Control per the QMP would lead to poor quality work on the Project, reduced confidence of the public, increased life cycle costs | Construction
Initial |  | I-70 East |  | CO |  | Quality Management Plan integration with project | As a result developer not following the Quality Asurrance and Quality Control requirements in the Project Agreement would lead to reduced quality | Construction
Initial |  | I-70 East |  | CO |  | Owner / Consultant communication | As a result of lack of collocation between stakeholders during procurement phase would lead to discrepencies/inconsistencies in the RFP and missed deadlines | Stakeholder
Initial |  | I-70 East |  | CO |  | Railway bridge type and construction unknown | As a result of railroad plans not complete would lead to additional costs and schedule delays | Design
Initial |  | I-70 East |  | CO |  | Stakeholder lead agreement | As a result of agreement not complete would lead to additional costs and schedule delays due to unknown terms and conditions | Stakeholder
Initial |  | I-70 East |  | CO |  | Conflicts in design requirements | As a result of inconsistencies in Contract documents would lead to potential change order during construction | Design
Initial |  | I-70 East |  | CO |  | Technical advances during project - allow for innovation | As a result of project requirements written too prescriptive or does not accommodate innovation | Design
Initial |  | I-70 East |  | CO |  | Develop project specific criteria and scope | As a result of insufficient information provided with proposal to define project scope would lead to additional costs (by way of high proposer prices or change orders) and schedule delays | Management and Funding
Initial |  | I-70 East |  | CO |  | Additional Right of way is required | As a result of limited Right of way available between Brighton and Colorado Blvds would lead to additional costs to relocate business and purchase Right of way parcel. Business closes - loss of jobs and tax revenue. | Right of way
Initial |  | I-70 East |  | CO |  | Final product does not do anything for congestion | As a result of implemented alternative does not improve existing condition would lead to potential lawsuits for congestion | Traffic
Initial |  | I-70 East |  | CO |  | New owner (Colorado DOT) director | As a result of new CDOT director not supportive of Project would lead to delay or termination of the Project | Organizational
Initial |  | I-70 East |  | CO |  | Management experience with Alternative Procurement Delivery | As a result of lack of CDOT experience with selected delivery (alternative project delivery) method would lead to unsuccessful procurement and/or project | Procurement and contracting
Initial |  | I-70 East |  | CO |  | owner - CDOT resource availability | As a result of CDOT staff committed to other projects would lead to inadequate CDOT staffing to manage the project during procurement and construction | Organizational
Initial |  | I-70 East |  | CO |  | Public with Owner and Concessionaire communications | As a result of Blended Public Involvement process would lead to confusion on responsibilities and inaccurate information being distributed to the public | Stakeholder
Initial |  | I-70 East |  | CO |  | Scope change | As a result of UPRR scope changes and multiple plan reviews would lead to additional cost and schedule delays | Management and Funding
Initial |  | I-70 East |  | CO |  | Scope change | As a result of BNSF scope changes and multiple plan reviews would lead to additional cost and schedule delays | Management and Funding
Initial |  | I-70 East |  | CO |  | Scope change | As a result of DRIR scope changes and multiple plan reviews would lead to additional cost and schedule delays | Management and Funding
Initial |  | I-70 East |  | CO |  | Documentation and Quality Control | As a result of developer not managing per the Quality control and inssurance would lead to additional schedule delays if submittals not provided or reviewed in a timely fashion | Construction
Initial |  | I-70 East |  | CO |  | Decision making process - project | As a result of unclear roles and responsibilities among project team would lead to additional schedule delays if submittals not provided or reviewed in a timely fashion | Management and Funding
Initial |  | I-70 East |  | CO |  | Design Optimization related cost savings | As a result of developer design modifications/efficiencies would lead to reduction in Project Agreement price | Design
Initial |  | I-70 East |  | CO |  | Owner approval of railroad crossings | As a result of third party or railroad interference or opposition would lead to additional cost and schedule delays | Right of way
Initial |  | I-70 East |  | CO |  | Utility relocation | As a result of UPRR relocation not complete would lead to additional cost and schedule delays | Utilities
Initial |  | I-70 East |  | CO |  | Utility coordination | As a result of unidentified utilities within project limits would lead to additional cost and schedule delays | Utilities
Initial |  | I-70 East |  | CO |  | Utility companies not meeting commitments | As a result of utility companies missing deadlines for relocation activities (design and construction) would lead to additional cost and schedule delays | Utilities
Initial |  | I-70 East |  | CO |  | Developer requesting change orders due to third party requests | As a result of third party staff adding scope or directing Developer work during construction inspections and design reviews would lead to additional cost and schedule delays | Management and Funding
Initial |  | I-70 East |  | CO |  | Developer schedule exposes owner to risk of unsubstantiated schedule delays | As a result of developer preliminary or baseline schedule is inaccurate or poorly constructed would lead to additional cost and schedule delays | Construction
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Pavement Design | Accounts for savings due to use of asphalt instead of concrete. Base estimate assumes concrete. | Design
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Complex Structure Optimization and Design on I-285/SR400 Interchange | Accounts for savings due to optimizing structure quantities. Options may include optimizing borrow, structure, and wall quantities, changes in structure types, and prefabricated members. Risk assumes maximum impact of 25% of steel bridge construction cost ($45M). | Design
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Rock Excavation | Accounts for additional cost due to increase rock excuvation identified on SR400. Risk based on impact to 10,000 to 20,000 CY at $20/CY (10% of total excuvation cost). | Structure and Geotechnical
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Erosion Control - I-285/SR400 Interchange | Accounts for additional cost due to increase erosion control quantities for I-284/SR400 Interchange. | Structure and Geotechnical
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Erosion Control - SR400 | Accounts for additional cost due to increase erosion control quantities on SR400. | Structure and Geotechnical
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Public Involvement - I-285/SR400 Interchange | Accounts for additional cost due to public involvement on I-285/SR400 Interchange. | Stakeholder
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Public Involvement - SR400 | Accounts for additional cost due to scope modifications on SR400 due to public involvement commitments. | Stakeholder
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Additional Mobilization and Traffic Control on I-285/SR400 Interchange | Accounts for additional cost due to increase mobilization and traffic control on I-284/SR400 Interchange. | Traffic
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Additional Mobilization and Traffic Control on SR400 Lanes | Accounts for additional cost due to increase mobilization and traffic control on SR400. | Traffic
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Geotechnical | Accounts for geotechnical issues on I-285/SR400 Interchange. Risk assumes 25% of complex structures ($45M) as maximum impact. | Structure and Geotechnical
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Retaining Wall and foundation Optimization - SR400 Lanes | Accounts for savings due to optimization of wall quantities and types such soil nail walls to conventional wall. Risk assumes 15% of soil nail wall cost ($14.5M) as maximum impact. | Structure and Geotechnical
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Retaining Wall and foundation Optimization - I-285/SR400 Interchange | Accounts for savings due to optimization of wall quantities and types such soil nail walls to conventional wall. Risk assumes 15% of soil nail wall cost ($21.5M) as maximum impact. | Structure and Geotechnical
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | SR 400 Lanes Noise Walls | Accounts for savings due to optimization of noise wall quantities and reduced unit prices. | Environmental
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | I-285/SR400 Interchange Noise Walls | Accounts for savings due to reduced noise wall unit prices. | Environmental
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Design Optimization - SR400 CD Lanes | Accounts for savings due to optimization of grade aggregate base quantities by improving subgrade | Design
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Design Optimization - I-285/SR400 Interchange | Accounts for savings due to optimization of grade aggregate base quantities by improving subgrade | Design
Initial |  | I-285/SR 400 Interchange Project | SR400 CD Lanes | GA |  | Hazardous Materials - SR400 CD Lanes | Accounts for additional cost due to the identification and disposal of hazardous materials on SR400 CD Lanes as related to utlity relocations and environment commitments. | Environmental
Initial |  | I-285/SR 400 Interchange Project | I-285/SR400 Interchange | GA |  | Hazardous Materials - I-285/SR400 Interchange | Accounts for additional cost due to the identification and disposal of hazardous materials on I-285/SR400 Interchangeas related to utlity relocations and environment commitments. | Environmental
Initial |  | I-75 Modernization | Segment 3 | MI |  | Potential additional Right of Way costs, e.g. condemnation cases. | Potential additional Right of Way costs, e.g. condemnation cases. | Right of Way
Initial |  | I-75 Modernization | Segment 3 | MI |  | Compressed construction schedule | Compressed construction schedule | Construction
Second |  | I-75 Modernization |  | MI |  | Work within existing footprint, contractor to prepare final design | Constructability of Design | Design
Second |  | I-75 Modernization |  | MI |  | Work within existing footprint, contractor to prepare final design | Constructability of Design | Design
Second |  | I-75 Modernization |  | MI |  | Design oversights may cause additional costs and delays during design, construction and operations phases | Design interfaces and quality issues | Design
Second |  | I-75 Modernization |  | MI |  | Design oversights may cause additional costs and delays during design, construction and operations phases | Design interfaces and quality issues | Design
Second |  | I-75 Modernization |  | MI |  | Evolving project definition leads to design related scope creep | Definition of Scope | Design
Second |  | I-75 Modernization |  | MI |  | Evolving project definition leads to design related scope creep | Definition of Scope | Design
Second |  | I-75 Modernization |  | MI |  | Design packages omit necessary project elements | Scope gaps between contractors | Design
Second |  | I-75 Modernization |  | MI |  | Design packages omit necessary project elements | Scope gaps between contractors | Design
Second |  | I-75 Modernization |  | MI |  | Owner directed changes lead to costly construction overruns | Definition of Scope | Management and Funding
Second |  | I-75 Modernization |  | MI |  | Owner directed changes lead to costly construction overruns | Definition of Scope | Management and Funding
Second |  | I-75 Modernization |  | MI |  | Unknown subsurface conditions cause delay or cost increase | Different site and subsurface condition | Construction
Second |  | I-75 Modernization |  | MI |  | Unknown subsurface conditions cause delay or cost increase | Different site and subsurface condition | Construction
Second |  | I-75 Modernization |  | MI |  | Coordination and delays with utility relocation | Utility coordination and Delays | Utilities
Second |  | I-75 Modernization |  | MI |  | Coordination and delays with utility relocation | Utility coordination and Delays | Utilities
Second |  | I-75 Modernization |  | MI |  | Damage to unknown utilities | Unknown Utilities | Utilities
Second |  | I-75 Modernization |  | MI |  | Damage to unknown utilities | Unknown Utilities | Utilities
Second |  | I-75 Modernization |  | MI |  | Commodity price escalation increases project costs | Commodity inflation | Management and Funding
Second |  | I-75 Modernization |  | MI |  | Commodity price escalation increases project costs | Commodity inflation | Management and Funding
Second |  | I-75 Modernization |  | MI |  | Labor escalation increases project costs | Labor inflamation | Management and Funding
Second |  | I-75 Modernization |  | MI |  | Labor escalation increases project costs | Labor inflamation | Management and Funding
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Conflict with EPA dredging contractor | Conflict with EPA dredging contractor | Stakeholder
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Conflict with EPA dredging contractor | Conflict with EPA dredging contractor | Stakeholder
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Lack of planning for future land use under the bridge could lead to undesirable conditions post construction | Lack of planning for future land use under the bridge could lead to undesirable conditions post construction | Traffic
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Lack of planning for future land use under the bridge could lead to undesirable conditions post construction | Lack of planning for future land use under the bridge could lead to undesirable conditions post construction | Traffic
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in securing Phelps Dodge approval and cooperation regarding capping of property and access to property | Delay in securing Phelps Dodge approval and cooperation regarding capping of property and access to property | Right of Way
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in securing Phelps Dodge approval and cooperation regarding capping of property and access to property | Delay in securing Phelps Dodge approval and cooperation regarding capping of property and access to property | Right of Way
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Damage to existing structures during construction (bridge, utilities, cemetery, buildings, etc.) | Damage to existing structures during construction (bridge, utilities, cemetery, buildings, etc.) | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Damage to existing structures during construction (bridge, utilities, cemetery, buildings, etc.) | Damage to existing structures during construction (bridge, utilities, cemetery, buildings, etc.) | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Insufficient time to review and approve design leads to errors | Insufficient time to review and approve design leads to errors | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Insufficient time to review and approve design leads to errors | Insufficient time to review and approve design leads to errors | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Lack of prescriptive design requirements leads to dispute of project requirements and claims from Design Builder | Lack of prescriptive design requirements leads to dispute of project requirements and claims from Design Builder | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Lack of prescriptive design requirements leads to dispute of project requirements and claims from Design Builder | Lack of prescriptive design requirements leads to dispute of project requirements and claims from Design Builder | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Error in Directive Plans (alignment and profile) | Error in Directive Plans (alignment and profile) | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Error in Directive Plans (alignment and profile) | Error in Directive Plans (alignment and profile) | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | DOT’s lack of experience with Cable-Stayed bridges could lead to poor decisions and higher O&M costs | DOT’s lack of experience with Cable-Stayed bridges could lead to poor decisions and higher O&M costs | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | DOT’s lack of experience with Cable-Stayed bridges could lead to poor decisions and higher O&M costs | DOT’s lack of experience with Cable-Stayed bridges could lead to poor decisions and higher O&M costs | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delays in utility relocations due to delay in field work required from utility owners | Delays in utility relocations due to delay in field work required from utility owners | Utilities
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delays in utility relocations due to delay in field work required from utility owners | Delays in utility relocations due to delay in field work required from utility owners | Utilities
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in obtaining Environmental Permits | Delay in obtaining Environmental Permits | Environmental
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in obtaining Environmental Permits | Delay in obtaining Environmental Permits | Environmental
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Design modifications are required by Design Builder | Design modifications are required by Design Builder | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Design modifications are required by Design Builder | Design modifications are required by Design Builder | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Design and Construction of Eastbound structure results in inefficiencies or constructability issues for future Westbound structure | Design and Construction of Eastbound structure results in inefficiencies or constructability issues for future Westbound structure | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Design and Construction of Eastbound structure results in inefficiencies or constructability issues for future Westbound structure | Design and Construction of Eastbound structure results in inefficiencies or constructability issues for future Westbound structure | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Lack of appropriate DOT staff to review Proposals and ATCs could result in poor decisions and delays in procurement. | Lack of appropriate DOT staff to review Proposals and ATCs could result in poor decisions and delays in procurement. | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Lack of appropriate DOT staff to review Proposals and ATCs could result in poor decisions and delays in procurement. | Lack of appropriate DOT staff to review Proposals and ATCs could result in poor decisions and delays in procurement. | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in acquisition of temporary easements | Delay in acquisition of temporary easements | Right of Way
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in acquisition of temporary easements | Delay in acquisition of temporary easements | Right of Way
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in tenant relocations | Delay in tenant relocations | Right of Way
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in tenant relocations | Delay in tenant relocations | Right of Way
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in obtaining utility owner approvals | Delay in obtaining utility owner approvals | Utilities
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in obtaining utility owner approvals | Delay in obtaining utility owner approvals | Utilities
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Environmental Permits obtained by NYSDOT include stringent restrictions | Environmental Permits obtained by NYSDOT include stringent restrictions | Environmental
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Environmental Permits obtained by NYSDOT include stringent restrictions | Environmental Permits obtained by NYSDOT include stringent restrictions | Environmental
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Construction interface issues with NYSDOT bridge repair contractor | Construction interface issues with NYSDOT bridge repair contractor | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Construction interface issues with NYSDOT bridge repair contractor | Construction interface issues with NYSDOT bridge repair contractor | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Worker injury during construction or OSHA violation | Worker injury during construction or OSHA violation | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Worker injury during construction or OSHA violation | Worker injury during construction or OSHA violation | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Aggressive procurement schedule could result in low quality and high cost bids. | Aggressive procurement schedule could result in low quality and high cost bids. | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Aggressive procurement schedule could result in low quality and high cost bids. | Aggressive procurement schedule could result in low quality and high cost bids. | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Labor Strike | Labor Strike | Management and Funding
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Labor Strike | Labor Strike | Management and Funding
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Fraud on behalf of the contractor on what work has been completed and on the quality of that work | Fraud on behalf of the contractor on what work has been completed and on the quality of that work | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Fraud on behalf of the contractor on what work has been completed and on the quality of that work | Fraud on behalf of the contractor on what work has been completed and on the quality of that work | Construction
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | DOT overtime restrictions on staff could lead to delays | DOT overtime restrictions on staff could lead to delays | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | DOT overtime restrictions on staff could lead to delays | DOT overtime restrictions on staff could lead to delays | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Local road reconstruction limits extend beyond currently anticipated construction limits | Local road reconstruction limits extend beyond currently anticipated construction limits | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Local road reconstruction limits extend beyond currently anticipated construction limits | Local road reconstruction limits extend beyond currently anticipated construction limits | Organizational
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in obtaining Environmental approvals | Delay in obtaining Environmental approvals | Environmental
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Delay in obtaining Environmental approvals | Delay in obtaining Environmental approvals | Environmental
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Wind studies completed during the design phase are insufficient for all stages of construction (existing bridge removed, new WB bridge in place) | Wind studies completed during the design phase are insufficient for all stages of construction (existing bridge removed, new WB bridge in place) | Design
Initial |  | Kosciuszko Bridge Replacement, I-278 over Newtown Creek |  | NY |  | Wind studies completed during the design phase are insufficient for all stages of construction (existing bridge removed, new WB bridge in place) | Wind studies completed during the design phase are insufficient for all stages of construction (existing bridge removed, new WB bridge in place) | Design
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES01 | Incorrect Definition of Subsurface Conditions Based on Initial Boring Program | Incorrect Definition of Subsurface Conditions Based on Initial Boring Program | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES02 | Approval for Design Exceptions - Conceptual Design - Need to submit to FHWA - have had initial discussions | Approval for Design Exceptions - Conceptual Design - Need to submit to FHWA - have had initial discussions | Design
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES03 | Approval for Design Exceptions - DBC Design - Any additional DE's related to DBC's final design | Approval for Design Exceptions - DBC Design - Any additional DE's related to DBC's final design | Design
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES05 | Owner Review Time - RFP commits to a 21 Day review period. | Owner Review Time - RFP commits to a 21 Day review period. | Stakeholder
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES06 | Environmental - Schedule delay to commencing permit application submission | Environmental - Schedule delay to commencing permit application submission | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES08 | quality control - DBC task | quality control - DBC task | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES09 | quality insurance - DBC task | quality insurance - DBC task | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES10 | Constructability of Design | Constructability of Design | Design
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES11 | Third Party Approvals - Utilities, Permitting Agencies, Government Entities, Etc | Third Party Approvals - Utilities, Permitting Agencies, Government Entities, Etc | Stakeholder
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES12 | Aesthetic Criteria | Aesthetic Criteria | Design
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES13 | Changes to Design Standards | Changes to Design Standards | Design
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES14 | Design Development from 30% to 100% Plans | Design Development from 30% to 100% Plans | Design
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | DES15 | Impacts due to other project interfaces | Impacts due to other project interfaces | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | GEO01 | Geotech Investigation - Borings based on Preliminary Design | Geotech Investigation - Borings based on Preliminary Design | Structure and Geotechnical
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | GEO02 | Time for geotechnical investigation | Time for geotechnical investigation | Structure and Geotechnical
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | RW01 | Right of way Plan Approval | Right of Way Plan Approval | Right of Way
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | RW02 | Right of way relocation due to Base Concept Design Change | Right of Way relocation due to Base Concept Design Change | Right of Way
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | RW04 | Access to right of way | Access to right of way | Right of Way
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | RW05 | Construction Easements | Construction Easements | Right of Way
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | RW07 | Utility Relocations | Utility Relocations | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | RW09 | Acquire additional right of way due to Design changes | Acquire additional RW due to Design changes | Right of Way
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV01 | Define Initial Enviromental Impacts | Define Initial Enviromental Impacts | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV02 | Define Environmental Parameters for Impacts | Define Environmental Parameters for Impacts | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV03 | Environmental Investigation | Environmental Investigation | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV04 | Contaminated Materials Estimates | Contaminated Materials Estimates | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV05 | Accuracy of Hazardous Survey information (Ph. 1 & 2 Assessments) | Accuracy of Hazardous Survey information (Ph. 1 & 2 Assessments) | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV06 | Environmental Permit Acquisition - DDOT | Environmental Permit Acquisition - DDOT | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV07 | Environmental Permit Acquistion - DB Contractor | Environmental Permit Acquistion - DB Contractor | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV08 | Environmental Mitigation Requirements | Environmental Mitigation Requirements | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV10 | Environmental Compliance - Known permit conditions/restrictions - Unexpected permit conditions | Environmental Compliance - Known permit conditions/restrictions - Unexpected permit conditions | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV11 | Permit Modifications Revisions During Construction | Permit Modifications Revisions During Construction | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV12 | Known Hazardous Mitigation | Known HazMat Mitigation | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV13 | Unknown Hazardous Mitigation | Unknown HazMat Mitigation | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | ENV14 | Hazardous Mitigation-Disposal-Transport Permits | Hazardous Mitigation-Disposal-Transport Permits | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT01 | Establish Existing Utility Locations | Establish Existing Utility Locations | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT02 | Define Existing Utility Relocation Needs Per Conceptual Design | Define Existing Utility Relocation Needs Per Conceptual Design | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT03 | Relocation of Utilities Prior to Construction | Relocation of Utilities Prior to Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT04 | Relocation of Utilities During Construction | Relocation of Utilities During Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT05 | Utility Coordination | Utility Coordination | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT06 | Damage to Known Utilities During Construction | Damage to Known Utilities During Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT07 | Damage to Unknown Utilities During Construction | Damage to Unknown Utilities During Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT08 | Utility Owner | Utility Owner | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT09 | Delays due to Unknowns Utility Conflicts | Delays due to Unknowns Utility Conflicts | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT10 | Third Party Agreements | Third Party Agreements | Stakeholder
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT11 | Utility Coordinating with Third Parties | Utility Coordinating with Third Parties | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT13 | Coordinating with Third Parties for Utilities | Coordinating with Third Parties for Utilities | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT14 | Coordination with Other Projects Adjacent Land Owners | Coordination with Other Projects Adjacent Land Owners | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT15 | DC Water Clean Rivers Tunnels Conflicts | DC Water Clean Rivers Tunnels Conflicts | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT17 | Utility Nu Star Fuel Pier at JBAB | Utility Nu Star Fuel Pier at JBAB | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT18 | Utility Nu Star Fuel Line | Utility Nu Star Fuel Line | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | UT21 | PEPCO utility Transmission | PEPCO Transmission | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN01 | Safety | Safety | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN02 | Construction Quality | Construction Quality | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN03 | Schedule (Realistic/Achievable) | Schedule (Realistic/Achievable) | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN04 | Materials Quality | Materials Quality | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN05 | Materials Documentation | Materials Documentation | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN06 | Material Availability | Material Availability | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN07 | Construction quality control | Construction Quality Control | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN08 | Construction quality assurance | Construction Quality Aurrance | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN09 | Erosion Control | Erosion Control | Structure and Geotechnical
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN11 | Accidents Within the Work Zone - Liability | Accidents Within the Work Zone - Liability | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN12 | Utility Third Party Damages | Utility Third Party Damages | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN14 | Maintenance of Traffic | Maintenance of Traffic | Traffic
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN15 | Work Methods | Work Methods | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN16 | Detour Routes | Detour Routes | Traffic
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN17 | Labor Shortage | Labor Shortage | Management and Funding
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN18 | Differing Site Conditions | Differing Site Conditions | Construction
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN19 | Construction Noise | Construction Noise | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN20 | Community Relations | Community Relations | Stakeholder
Initial |  | South Capitol Street Corridor Project | Segments 1&2 | DC | CN21 | Fuel Steel Asphalt fluctuation of Price Indices | Fuel Steel Asphalt fluctuation of Price Indices | Management and Funding
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES01 | Incorrect Definition of Subsurface Conditions Based on Initial Boring Program | Incorrect Definition of Subsurface Conditions Based on Initial Boring Program | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES02 | Determination of needed Design Exceptions - Conceptual Design - Need to submit to FHWA for approval | Determination of needed Design Exceptions - Conceptual Design - Need to submit to FHWA for approval | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES03 | Approval for Design Exceptions - DBC Design - Only if project delivery method is DB | Approval for Design Exceptions - DBC Design - Only if project delivery method is DB | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES04 | Owner Review Time for design approval - RFP commits to a 21 Day review period. | Owner Review Time for design approval - RFP commits to a 21 Day review period. | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES05 | ROD Executed - Schedule delay to commencing permit application submission | ROD Executed - Schedule delay to commencing permit application submission | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES07 | Design quality control- DBC task | Design Quality Control - DBC task | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES08 | Design quality assurance - DBC task | Design Quality Aurrance - DBC task | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES09 | Constructability of Design | Constructability of Design | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES10 | Third Party Approvals - Utilities, Permitting Agencies, Government Entities, Etc | Third Party Approvals - Utilities, Permitting Agencies, Government Entities, Etc | Stakeholder
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES11 | Aesthetic Criteria | Aesthetic Criteria | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES12 | Historic Preservation | Historic Preservation | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES13 | Changes to Design Standards | Changes to Design Standards | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES14 | Design Development from 10% to 100% Plans | Design Development from 10% to 100% Plans | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES15 | Changes to M Street at grade intersection | Changes to M Street at grade intersection | Design
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | DES16 | Impacts due to other project interfaces | Impacts due to other project interfaces | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | GEO1 | Geotech Investigation | Geotech Investigation | Structure and Geotechnical
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | RW01 | right of way Plan Approval | Right of Way Plan Approval | Right of Way
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | RW02 | right of way Change due to Base Concept Design Change | Right of Way Change due to Base Concept Design Change | Right of Way
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV01 | Define Initial Enviromental Impacts | Define Initial Enviromental Impacts | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV02 | Define Parameters for Environmental Impacts | Define Parameters for Environmental Impacts | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV03 | Environmental Investigation | Environmental Investigation | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV04 | Contaminated Materials Estimates | Contaminated Materials Estimates | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV05 | Accuracy of Hazardous materials Survey information (Ph. 1 & 2 Assessments) | Accuracy of Hazardous materials Survey information (Ph. 1 & 2 Assessments) | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV06 | Environmental Permit Acquisition - DDOT | Environmental Permit Acquisition - DDOT | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV07 | Environmental Permit Acquistion - DB Contractor | Environmental Permit Acquistion - DB Contractor | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV08 | Environmental Mitigation and Mitigation Requirements | Environmental Mitigation and Mitigation Requirements | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV10 | Environmental Compliance - Known permit conditions/restrictions - Unexpected permit conditions | Environmental Compliance - Known permit conditions/restrictions - Unexpected permit conditions | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV11 | Environmental Permit Modifications and Revisions During Construction | Environmental Permit Modifications/Revisions During Construction | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV12 | Known Hazardous materials Mitigation | Known Hazardous materials Mitigation | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV13 | Unknown Hazardous materials Mitigation | Unknown Hazardous materials Mitigation | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | ENV14 | Hazardous materials Mitigation-Disposal-Transport Permits | Hazardous materials Mitigation-Disposal-Transport Permits | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT01 | Establish Existing Utility Locations and Conditions | Establish Existing Utility Locations and Conditions | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT02 | Define Existing Utility Relocation Needs Per Conceptual Design | Define Existing Utility Relocation Needs Per Conceptual Design | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT03 | Relocation of Utilities Prior to Construction | Relocation of Utilities Prior to Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT04 | Relocation of Utilities During Construction | Relocation of Utilities During Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT05 | Utility Coordination | Utility Coordination | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT06 | Damage to Known Utilities During Construction | Damage to Known Utilities During Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT07 | Damage to Unknown Utilities During Construction | Damage to Unknown Utilities During Construction | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT08 | Utility Owner Third Party Caused Related Delays | Utility Owner Third Party Caused Related Delays | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT09 | Delays due to Unknowns | Delays due to Unknowns | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT10 | Third Party Agreements | Third Party Agreements | Stakeholder
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT11 | Utilities Coordinating with Third Parties | Utilities Coordinating with Third Parties | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT13 | Utility Coordinating with Third Parties for Betterments | Utility Coordinating with Third Parties for Betterments | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT14 | Utility Coordination with Other Projects/Adjacent Land Owners | Utility Coordination with Other Projects/Adjacent Land Owners | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT15 | DC Water Clean Rivers Tunnels | DC Water Clean Rivers Tunnels | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | UT17 | PEPCO utility Transmission | PEPCO Transmission | Utilities
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN01 | Safety | Safety | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN02 | Construction Quality | Construction Quality | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN03 | Schedule (Realistic/Achievable) | Schedule (Realistic/Achievable) | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN04 | Materials Quality | Materials Quality | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN05 | Materials Quality Documentation | Materials Quality Documentation | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN06 | Material Availability | Material Availability | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN07 | Construction quality control | Construction QC | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN08 | Construction quality assurance | Construction QA | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN09 | Erosion Control | Erosion Control | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN11 | Accidents Within the Work Zone - Liability | Accidents Within the Work Zone - Liability | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN12 | Third Party Damages | Third Party Damages | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN14 | Maintenance of Traffic | Maintenance of Traffic | Traffic
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN15 | Work Methods | Work Methods | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN16 | Detour Routes | Detour Routes | Traffic
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN17 | Labor Shortage | Labor Shortage | Management and Funding
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN18 | Differing Site Conditions | Differing Site Conditions | Construction
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN19 | Construction Noise | Construction Noise | Environmental
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN20 | Community Relations | Community Relations | Stakeholder
Initial |  | South Capitol Street Corridor Project | Segments 3, 4 & 5 | DC | CN21 | Fuel Steel Asphalt fluctuation of Price Indices | Fuel Steel Asphalt fluctuation of Price Indices | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-10.01 | Additional maintenance of traffic costs over the base for STAR Interchange | The base has $1.2M for traffic control. The risk is an additional temporary lighting and other traffic control items will be added. | Traffic
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-10.02 | Opportunity to use existing I-15 pavement for detours because of the shifting of I-15 to the east | This is the base design. | Traffic
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-20.01 | Environmental permitting Issues (incl. work restrictions) | Construction is not schedule until 2018, not a risk at this time. | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-900.01 | Differing site conditions | There is a risk of a caliche but the risk is minimal | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-70.02 | With the change in design (I-15 being raised) there may be a potential issue with lack of state provided borrow material | This is not a risk at this time. This will need to be monitored. If the lack of state sources diminishes then commercial sources will be needed which may increase the cost of borrow. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-70.03 | Borrow material cost more than what is in the base | The base assumes states supply source at $7 a yard, if it is not sufficient state material available, a commercial source could be $12 a yard, the current need is 350,000 CY. | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-80.01 | Conflicts with other construction projects in the area | Desert Express or Las Vegas Blvd could be under construction during the same period, if so potential delays of up to 3 months over a 2 years period. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-90.01 | Contractor Access and Staging Coordination | Contractor Access and Staging Coordination | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.02 | Potential Changes to Roadway Design | A redesign may be required to accommodate Desert Express. This will require the shifting of I-15 alignment up to an additional 25 feet to the east. This will require redesign and the cost of any additional ROW. This shifts the Project outside of the footprint within the current NEPA document and which could trigger a revaluation. An additional $13.5M for ROW, includes $6M for billboards, and $2.5M for engineering. Added cost for MSE walls and extending ramps could cost $3M. The current design schedule would allow time for this redesign. If this risk occurs the cost would be paid by the Desert Express. (DO NOT MODEL) | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.03 | Landscaping and Aesthetics | Cost of Landscaping & Aesthetics exceeds the base. NDOT requirements is 3% of construction cost, there is little no risk of exceeding this number. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-20.01 | Approval of Design Exceptions | Has no design exceptions, with the current design. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-40.01 | Additional Scope driven by Stakeholders | Request for enhancements from the city of Henderson or Clark County. | Stakeholder
Initial |  | I-15 South Corridor Improvements Project |  | NV | ENV-10.01 | National Environmental Policy Act Review (NEPA) re-approval for Starr Interchange | National Environmental Policy Act Review (NEPA) document has a SPUI type interchange as the preferred alternative. The current design is tight urban diamond with the I-15 alignment shifted 50 feet to the east | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-30.01 | Limited Access (Change of Access) | A Corridor wide access report that included Starr has already been approved. A new access report that includes cactus and Starr is currently under way. Minimal risk at this time to Starr. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-40.01 | Stakeholders request additional access at Starr Interchange | Ensworth (Frank Sinatra) may be extended through the project before it begins. Ensworth is not within the scope of this project. The cost to construct this is approximately $2.7M. This currently not a risk to this project. | Stakeholder
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-50.01 | Opportunity for donation of some right of way by owners (East to West) | The Right of Way for Starr Avenue may be donated, 2400 feet long by 50 feet wide on the North Side of the Starr Avenue Alignment, assumed $12 per square foot. | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-50.02 | Development east of I-15 happens prior to Starr interchange project leading to donation of right of way (North | This would lead the county to make developers donate portion of ROW to Starr project so ROW would be lower than the base | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-60.01 | Additional Right of Way is required | May need to acquire property in the southeast quadrant in the interchange (approx. 2.5 acres) | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | STG-10.01 | Potential Changes to Structures Design | There is an opportunity to go to a two span structure which would reduce structural depth and earthwork. It can also reduce foundational loads and allows the use of spread footings. We can reduce the structural cost by $60 a square foot. Could reduce the amount of borrow needed by 20,000 CY. There is a low likelihood due to potential conflict with water line and left turn pockets. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | STG-20.01 | Potential Changes to Geotechnical Design for foundations | Cactus is on spread footings, there is a chance that spread footing is used in lieu of drilled shafts. This risk is mutually exclusive to risk STG 10.01 | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | UTL-10.01 | Utility Design Coordination and Agreements | Easement will be with Nevada Energy for power to billboard | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | UTL-20.01 | Utility conflicts | Other than the waterline which is not impacted by the base design there are no utility relocations or conflicts. | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-10.01 | Additional Maintenance of Traffic costs over the base for SLOAN interchange | The base has $3M for traffic control. This appears to be adequate at this time. | Traffic
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-20.01 | Environmental Construction Permitting Issues (incl. work restrictions) | Environmental Construction Permitting Issues (incl. work restrictions) | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-900.01 | Differing Site Conditions | There is a risk of a caliche but the risk is minimal. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-70.03 | Borrow Material Cost | The base assumes; states supply source at $7-$8 a yard. If it is not sufficient, then state material is available, a commercial source could be $12 a yard (315,000 CY). | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-80.01 | Potential Conflicts with other construction Projects in the area. | Desert Express or Las Vegas Blvd could be under construction during the same period, if so; potential delays of up to 3 months over a 2 years period. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-90.01 | Contractor Access and Staging Coordination and Constructability Issues | Contractor Access and Staging Coordination and Constructability Issues | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.03 | Potential Changes due to Value Engineering. | Value Engineering typically can reduce the construction cost by 10%,. This is mutually exclusive to all other opportunities | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.04 | Landscaping and Aesthetics | Cost of Landscaping & Aesthetics exceeds the base. NDOT requirements is; 3% of construction cost, there is no risk of exceeding this number. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | ENV-90.01 | Sound walls may be needed | The enviornmental document did not identify walls in the area. If the area surrounding the site of the interchange developments prior to the construction of the interchange, sound walls may be needed to mitigate for increased noise levels. | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-20.01 | Approval of Design Exceptions | Approval of Design Exceptions | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | PSP-30.02 | Potential Scope changes driven by Stake Holders. | There is a likelihood of potential scope creep due to no development today, and a probability of development by the time the project is constructed. | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-30.01 | right of way Acquisition Issues | The base estimate assumes $12 SF, CACTUS has some acquisitions as low as $6 SF, and depending on development it can go higher. | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-10.01 | Reduced need for right of way | The Right of Way impacts may be able to be reduced. Therefore, there is an opportunity to reduce ROW costs. | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-50.02 | Relocation of Utilities | Currently there are 3 utilities line in the vicinity of the Interchange that may need to be relocated. | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | STG-10.02 | Potential Changes to Geotechnical Design for foundations | There is an opportunity for spread footings, but it is covered in other structure opportunities | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | UTL-10.01 | Utility easement required for Power Into the Project | Potential to go out for half a mile more than the base for a 10 foot permanent easement, and a 10 foot for temporary easement. Also the Cost of bringing the power in is $50 a foot. | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | UTL-20.01 | Utility conflicts | No utility information is available, we are constructing outside of our existing ROW, and there is a risk of having utility conflicts. The highest cost risk will be the gas or petroleum line. | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-10.01 | Additional Maintenance of Traffic costs over the base for BERMUDA Interchange | The base has $2M for traffic control. This appears to be adequate at this time. | Traffic
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-20.01 | Environemntal Permitting Issues (incl. work restrictions) | Environemntal Permitting Issues (incl. work restrictions) | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-900.01 | Differing Site Conditions | Differing Site Conditions | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-70.03 | Borrow Material Cost | The base assumes; states supply source at $7-$8 a yard. If it is not sufficient, then state material is available, a commercial source could be $12 a yard, and the current need is 290,000 CY. | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-80.01 | Potential conflicts with other Construction Projects in the area. | Desert express or Las Vegas Blvd could be under construction during the same period, if so; potential delays of up to 3 months over a 2 years period. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-90.01 | Contractor Access and Staging Coordination and Constructability Issues | No staging area has been Identified. The contractor may need to Lease adjacent land. Assume 2 acres at $2 to $5 SF. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.01 | Landscaping Aesthetics | Cost of Landscaping & Aesthetics will not exceed the base. NDOT requirements is 3% of construction cost, there is no risk of exceeding this number. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.02 | Opportunity that a tight diamond interchange will be built instead of a SPUI | May require a change in traffic analysis for feasibility, but the tight diamond would be cheaper than the base SPUI which is the assumed interchange type in the NEPA document. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.04 | Stakeholders request additional access at Bermuda Interchange | Not a risk at this time. | Stakeholder
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.05 | Potential Changes due to Value Engineering | Value Engineering typically can reduce the construction cost by 10%, the current design is fairly conservative. This is mutually exclusive to the risk DES 10.02 | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-20.01 | Approval of Design Exceptions | Approval of Design Exceptions | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | PSP-30.01 | Potential Scope changes driven by Stake Holders. | There is a likelihood of potential scope creep due to no development today, and a probability of development by the time the project is constructed. | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | ENV-90.01 | Sound walls may be needed | Sound walls currently not required in environmental document. If the area surrounding the site of the interchange developments prior to the construction of the interchange sound walls may be needed to mitigate for increased noise levels. | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-50.01 | right of way Acquisition Issues | The base estimate assumes $12 SF, CACTUS has some acquisitions as low as $6 SF, and depending on development it can go higher. | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | STG-10.02 | Potential Changes to Geotechnical Design for foundations | There is an Opportunity for Spread footings, but it is covered in other structure opportunities. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | UTL-20.01 | Utility conflicts | No utility information is available, we are constructing outside of our existing ROW, and there is a risk of having Utility Conflicts. | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | UTL-10.01 | Utility Easement Required Power Into the Project | Potential to go out for a half a mile more than the base for a 10 foot permanent easement, and a 10 foot for temporary easement. Also the cost of bringing the power in is $50 a foot. | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-10.01 | Traffic Control and Staging Issues (MOT/WZTC) | The estimate for traffic control is $175,000 for widening existing two lanes to four lanes. Since there will be considerable labor for traffic control, normally 5% of the construction costs assumed for traffic control. | Traffic
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-20.01 | Environmental Permitting Issues (incl. work restrictions) | Environmental Permitting Issues (incl. work restrictions) | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-900.01 | Differing Site Conditions | There is a risk of a caliche being present. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-90.01 | Contractor Access and Staging Coordination and Constructability Issues | Contractor Access and Staging Coordination and Constructability Issues | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-80.01 | Interference From other Construction Projects | The risk is a potential delay during construction. This project could be under construction while STARR Interchange is being built. Desert Express could also be under construction. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.01 | Potential Scope changes driven by Stake Holders. | There is a likelihood of potential scope creep due to no development today, and a probability of development by the time the project is constructed | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-20.01 | Approval of Design Exceptions | Approval of Design Exceptions | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | ENV-70.01 | Design Changes of Culverts | The price per LF in the 70% estimate is $370 to $1200 LF. The risk is bids will be much higher for these items. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-50.01 | right of way Acquisition Issues | right of way Acquisition Issues | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-60.01 | Additional right of way is required | Additional right of way is required | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | UTL-20.01 | Utility conflicts | No utility information is available, we are constructing outside of our existing ROW, and there is a risk of having utility conflicts. The base estimate has almost $6M Sewer, Water, and Power. The risk is additional utilities such as Fiber. | Utilities
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-10.01 | Traffic Control and Staging Issues (MOT/WZTC) | 10% of the construction cost is in the base estimate. The base seems to be sufficient, there is a slight risk that the contractors operations and delays could drive up the cost. | Traffic
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-20.01 | Environemntal Permitting Issues (incl. work restrictions) | Environemntal Permitting Issues (incl. work restrictions) | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-90.01 | Contractor Access and Staging Coordination and Constructability Issues | Contractor Access and Staging Coordination and Constructability Issues | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-900.01 | Differing Site Conditions | Differing Site Conditions | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.01 | Landscaping and Aesthetics | Cost of Landscaping & Aesthetics exceeds the base. NDOT requirements is up to 3% of construction cost, there is no risk of exceeding this number. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.02 | Design Changes because of Pavement Conditions | By the time the project is funded, the PCCP section from 215 to Tropicana may need major repairs as part of this improvement program, which could include replacement of some of the panels. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-20.01 | Approval of Design Exceptions | Approval of Design Exceptions | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | ENV-70.01 | Additional Enviromental Analysis | In the median along the horizontal curve of I-15 between St. Rose and Bermuda, the risk is additional Storm Sewer and drop Inlets will be needed in this area. | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-10.01 | Additional Maintenance of Traffic costs over the base for Phase 2B interchange | The base has $15M for traffic control. This section has the most complicated traffic control of the entire corridor. The replacement of the concrete panels that need to keep the ramps open for all of the Interchanges, and the cost of replacement of both bridges at Tropicana. A recent project requires 9 lanes to be open at the Tropicana. | Traffic
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-20.01 | Environemntal Permitting Issues (incl. work restrictions) | Environemntal Permitting Issues (incl. work restrictions) | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-900.01 | Differing Site Conditions | Differing Site Conditions | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-70.03 | Borrow Material Cost more than what is in the base. | The base assumes states supply source at $7-$8 a yard, if it is not sufficient state material available, a commercial source could be $12 a yard. | Management and Funding
Initial |  | I-15 South Corridor Improvements Project |  | NV | CNS-90.01 | Contractor Access and Staging Coordination and Constructability Issues | No staging area has been Identified in NEPA document. The contractor may need to Lease adjacent land. Assume 4 acres at $2 to $5 SF. | Construction
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.01 | Landscaping Aesthetics | Cost of landscaping & aesthetics will not exceed the base. NDOT requirements is 3% of construction cost, there is no risk of exceeding this number. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.01 | Potential Changes due to Value Engineering. | Value Engineering typically can reduce the construction cost by 10%, the current to design is fairly conservative. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-10.01 | Potential Changes to roadway Design | Risk is there may not have enough cover over Box Culvert Extensions. Assume 3 complete replacements at $1.5M each. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | DES-20.01 | Approval of Design Exceptions | A number of Design exceptions from Blue Diamond to Tropicana. The risk is an added cost for mitigation of the design exceptions. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | ENV-90.01 | Additional sound walls may be needed | The Enviromental document identifies some walls in the area. If the area surrounding the site of the widening along I-15 develops prior to the construction of the widening. Sound walls may be needed to mitigate for increased noise levels. | Environmental
Initial |  | I-15 South Corridor Improvements Project |  | NV | ROW-50.01 | Additional right of way is required | A possibility of additional Right of Way may be required in the vicinity of Tropicana I/C to accommodate the widening of the Tropicana structures. | Right of Way
Initial |  | I-15 South Corridor Improvements Project |  | NV | STG-10.01 | Potential Changes to Structures Design | Pressures to use accelerated bridge construction techniques or Pre-fabricated elements on the Tropicana structures. Most Likely based of $50 SF added cost, the high $85 SF added cost, and $40 SF for the Low added cost. | Design
Initial |  | I-15 South Corridor Improvements Project |  | NV | STG-20.01 | Potential Changes to Geotechnical Design for foundations | Assume Shafts for the structures. Not a Risk at this Time. | Design
Initial |  | Monroe Parkway Project |  | NC | A1 | Change in interchange configuration - US 74 Business (Stallings / Lake Park) | Change in interchange configuration - US 74 Business (Stallings / Lake Park) | Design
Initial |  | Monroe Parkway Project |  | NC | A2 | Change in interchange configuration - Indian Trail-Fairview Road | Change in interchange configuration - Indian Trail-Fairview Road | Design
Initial |  | Monroe Parkway Project |  | NC | A3 | Change in interchange configuration - Unionville-Indian Trail Road | Change in interchange configuration - Unionville-Indian Trail Road | Design
Initial |  | Monroe Parkway Project |  | NC | A4 | Change in interchange configuration - Rocky River Road | Change in interchange configuration - Rocky River Road | Design
Initial |  | Monroe Parkway Project |  | NC | A5 | Change in interchange configuration - US 601 | Change in interchange configuration - US 601 | Design
Initial |  | Monroe Parkway Project |  | NC | A6 | Change in interchange configuration - NC 200 (Morgan Mill Road) | Change in interchange configuration - NC 200 (Morgan Mill Road) | Design
Initial |  | Monroe Parkway Project |  | NC | A7 | Change in interchange configuration - Austin Chaney Road | Change in interchange configuration - Austin Chaney Road | Design
Initial |  | Monroe Parkway Project |  | NC | A8 | Change in interchange configuration - Forest Hills School Road | Change in interchange configuration - Forest Hills School Road | Design
Initial |  | Monroe Parkway Project |  | NC | A9 | Change in interchange configuration - US 74 (Marshville) | Change in interchange configuration - US 74 (Marshville) | Design
Initial |  | Monroe Parkway Project |  | NC | A10 | Change in tolling concept / design (e.g., don't use electronic toll collection) | Change in tolling concept / design (e.g., don't use electronic toll collection) | Traffic
Initial |  | Monroe Parkway Project |  | NC | A11 | Elevated section changes from retained fill to structure (e.g., hammerhead) | Elevated section changes from retained fill to structure (e.g., hammerhead) | Design
Initial |  | Monroe Parkway Project |  | NC | A12 | Change in design vicinity of McKee Road - developer impact / cost sharing | Change in design vicinity of McKee Road - developer impact / cost sharing | Design
Initial |  | Monroe Parkway Project |  | NC | A13 | Eliminate railroad crossing at Forest Hills School road | Eliminate railroad crossing at Forest Hills School road | Right of Way
Initial |  | Monroe Parkway Project |  | NC | A14 | Change in Design configuration - I485 | Change in Design configuration - I485 | Design
Initial |  | Monroe Parkway Project |  | NC | E1 | Delays securing conceptual Environemntal permits | Delays securing conceptual Environemntal permits | Environmental
Initial |  | Monroe Parkway Project |  | NC | E2 | Delays securing conceptual Environemntal permits | Delays securing conceptual Environemntal permits | Environmental
Initial |  | Monroe Parkway Project |  | NC | E4 | Approved Environmental permit conditions change, resulting in re-design | Approved Environmental permit conditions change, resulting in re-design | Environmental
Initial |  | Monroe Parkway Project |  | NC | E5 | Delayed Section 7 (biological) consultation for currently listed species | Delayed Section 7 (biological) consultation for currently listed species | Environmental
Initial |  | Monroe Parkway Project |  | NC | E6 | Delay to completion of Final Environmental Permits | Delay to completion of Final Environmental Permits | Environmental
Initial |  | Monroe Parkway Project |  | NC | E7 | Legal challenge to Environmental Permit | Legal challenge to Environmental Permit | Environmental
Initial |  | Monroe Parkway Project |  | NC | E8 | Additional or less noise mitigation required | Additional or less noise mitigation required | Environmental
Initial |  | Monroe Parkway Project |  | NC | E9 | Additional or less wetland mitigation required | Additional or less wetland mitigation required | Environmental
Initial |  | Monroe Parkway Project |  | NC | E10 | Additional or less stream mitigation required | Additional or less stream mitigation required | Environmental
Initial |  | Monroe Parkway Project |  | NC | E12 | Late definition of utility easements and relocation | Late definition of utility easements and relocation | Utilities
Initial |  | Monroe Parkway Project |  | NC | C1 | Encounter unanticipated utilities during construction | Encounter unanticipated utilities during construction | Utilities
Initial |  | Monroe Parkway Project |  | NC | C2 | Damage utilities during construction | Damage utilities during construction | Utilities
Initial |  | Monroe Parkway Project |  | NC | C3 | Encounter unanticipated contaminated or hazardous materials | Encounter unanticipated contaminated or hazardous materials | Utilities
Initial |  | Monroe Parkway Project |  | NC | C4 | Severe seasonal weather delays construction | Severe seasonal weather delays construction | Management and Funding
Initial |  | Monroe Parkway Project |  | NC | C5 | Significant weather event (e.g., hurricane) during construction | Significant weather event (e.g., hurricane) during construction | Management and Funding
Initial |  | Monroe Parkway Project |  | NC | C6 | Significant construction accident | Significant construction accident | Construction
Initial |  | Monroe Parkway Project |  | NC | C7 | Additional maintenance of traffic required | Additional maintenance of traffic required | Traffic
Initial |  | Monroe Parkway Project |  | NC | C8 | Different construction phasing than assumed – six-lane section / I-74 | Different construction phasing than assumed – six-lane section / I-74 | Construction
Initial |  | Monroe Parkway Project |  | NC | C9 | Different construction phasing than assumed – four-lane section | Different construction phasing than assumed – four-lane section | Construction
Initial |  | Monroe Parkway Project |  | NC | C10 | Ground conditions worse than assumed – bridge foundations | Ground conditions worse than assumed – bridge foundations | Construction
Initial |  | Monroe Parkway Project |  | NC | C11 | Ground conditions worse than assumed – embankment foundations | Ground conditions worse than assumed – embankment foundations | Construction
Initial |  | Monroe Parkway Project |  | NC | C12 | Delays to utility relocations – vicinity of elevated section | Delays to utility relocations – vicinity of elevated section | Utilities
Initial |  | Monroe Parkway Project |  | NC | C14 | Excessive groundwater in excavations | Excessive groundwater in excavations | Structure and Geotechnical
Initial |  | Monroe Parkway Project |  | NC | C15 | Additional species listed late in project (e.g., Savannah Lilliput mussel) | Additional species listed late in project (e.g., Savannah Lilliput mussel) | Environmental
Initial |  | Monroe Parkway Project |  | NC | C16 | Encounter unanticipated archaeological resource during construction | Encounter unanticipated archaeological resource during construction | Environmental
Initial |  | Monroe Parkway Project |  | NC | C17 | Encounter poor ground conditions during construction (not captured separately) | Encounter poor ground conditions during construction (not captured separately) | Construction
Initial |  | Monroe Parkway Project |  | NC | C18 | Increased aesthetics cost | Increased aesthetics cost | Design
Initial |  | Monroe Parkway Project |  | NC | C19 | Coordination issues between D/B and tolling contractors | Coordination issues between D/B and tolling contractors | Traffic
Initial |  | Monroe Parkway Project |  | NC | C20 | Additional or more detours Maintenance Of Traffic | Additional or more detours Maintenance Of Traffic | Traffic
Initial |  | Monroe Parkway Project |  | NC | C21 | Quality control | Quality control | Construction
Initial |  | Monroe Parkway Project |  | NC | C22 | Construction access (e.g., elevated 74) | Construction access (e.g., elevated 74) | Construction
Initial |  | Monroe Parkway Project |  | NC | C23 | Contractor and subcontractor termination because of poor performance | Contractor and subcontractor termination because of poor performance | Construction
Initial |  | Monroe Parkway Project |  | NC | C24 | Tolling system commissioning | Tolling system commissioning | Traffic
Initial |  | Monroe Parkway Project |  | NC | C25 | Unsuitable fill (waste some, more borrow) contaminated soils | Unsuitable fill (waste some, more borrow) contaminated soils | Environmental
Initial |  | St. Croix River Crossing | Debt | MN |  | Bond debt service comes out of highway revenue (costs resources for the organization) | Bond debt service comes out of highway revenue (costs resources for the organization) | Management and Funding
Initial |  | St. Croix River Crossing | Tolls | MN |  | Tolling success | Tolling success | Traffic
Initial |  | St. Croix River Crossing | Debt | MN |  | Creative financing will accelerate your funding base. | Creative financing will accelerate your funding base. | Management and Funding
Initial |  | St. Croix River Crossing | Debt | MN |  | Start construction and encounter some unforeseen surface condition (increase cost and delay project) | Start construction and encounter some unforeseen surface condition (increase cost and delay project) | Construction
Initial |  | St. Croix River Crossing | Tolls | MN |  | Accelerate project construction | Accelerate project construction | Construction
Initial |  | St. Croix River Crossing | Debt | MN |  | Non-recourse debt would not come out general highway revenue | Non-recourse debt would not come out general highway revenue | Management and Funding
Initial |  | St. Croix River Crossing | PPP | MN |  | Gov't looses control over use of facility - user fees | Gov't looses control over use of facility - user fees | Management and Funding
Initial |  | St. Croix River Crossing | Tolls | MN |  | Revenue sharing | Revenue sharing | Management and Funding
Initial |  | St. Croix River Crossing | Debt | MN |  | Project construction delay because of decision making | Project construction delay because of decision making | Management and Funding
Initial |  | St. Croix River Crossing | Debt | MN |  | More debt causes the need to find more revenues | More debt causes the need to find more revenues | Management and Funding
Initial |  | St. Croix River Crossing | Debt | MN |  | Delay in start of construction after debt has been achieved. | Delay in start of construction after debt has been achieved. | Management and Funding
Initial |  | St. Croix River Crossing | PPP | MN |  | tie user fees to inflation index | tie user fees to inflation index | Management and Funding
Initial |  | St. Croix River Crossing | PPP | MN |  | Construction acceleration thru design build project dekivery method | Construction acceleration thru design build project dekivery method | Procurement and contracting
Initial |  | St. Croix River Crossing | Debt | MN |  | Non-subordination clause if project becomes insolvent, bankrupt, or liquidated (TIFIA) | Non-subordination clause if project becomes insolvent, bankrupt, or liquidated (TIFIA) | Procurement and contracting
Initial |  | St. Croix River Crossing | Debt | MN |  | Project cost grows before you let the project. | Project cost grows before you let the project. | Management and Funding
Initial |  | St. Croix River Crossing | Tolls | MN |  | New Technology Fails | New Technology Fails | Construction
Initial |  | Centennial Corridor Project |  | CA |  | Pile driving noise and vibration | For example, due to vibration, noise, dust/air quality. Dust and noise should be covered by standard specs. Additional work restrictions (e.g., night work) may be involved. Vibration monitoring, damage not covered in the base. Pile driving is assumed on most structures, including the structures through the neighborhood sections. The City does advance inspections for cracks, etc. prior to construction. Property owners may make claims against the contractor due to vibration damage. | Structure and Geotechnical
Initial |  | Centennial Corridor Project |  | CA |  | Miscellaneous Change Orders / Claims (not captured elsewhere) | For example, due to design refinements, contract language. Experience on Westside Parkway has been about 5% of the contract, which is close to the Caltrans average. For example, a design change on the Centennial Project resulted in a design change to one of the structures. Differing site conditions issues have been experienced. | Procurement and contracting
Initial |  | Centennial Corridor Project |  | CA |  | Miscellaneous Change Orders / Claims (not captured elsewhere) | For example, due to design refinements, contract language. Experience on Westside Parkway has been about 5% of the contract, which is close to the Caltrans average. For example, a design change on the Centennial Project resulted in a design change to one of the structures. Differing site conditions issues have been experienced. | Procurement and contracting
Initial |  | Centennial Corridor Project |  | CA |  | Changed Bridge Foundation Design due to Geotechnical Information (other structures than addressed separately) | SR 99 flyover is addressed separately. Good soil conditions are generally anticipated in most areas where information is available (sandy loam soils prevalent along the river). Pile foundations have been assumed for most structures (spread footings are assumed for a few structures). However, future geotechnical investigations could indicate different conditions at some locations. Information along SR 58 and along SR 99 is available from as-builts. Limited data are available in the existing neighborhoods impacted. Pile depths of 80’-90’ assumed based on experience on Westside Parkway. However, limited information is available. Caltrans seismic design criteria require piles for magnitudes greater than 0.6g. The Bakersfield area is considered a moderate seismic zone. | Design
Initial |  | Centennial Corridor Project |  | CA |  | Opportunity for Retaining Wall Optimization | The current estimate assumes retaining walls will be constructed at the edge of ROW throughout the alignment. It may be possible, through additional analysis and design refinement, to optimize costs by adjusting wall types, trading ROW/slopes for costly walls, etc. Up to 30% of the walls could potentially be removed. Assume half of this cost could be saved as a net savings ($5-$6M). Also, wall types may be optimized (e.g., secant pile to CIP walls) to reduce costs. This opportunity has been realized and included in the base cost. Retire this opportunity. | Design
Initial |  | I-39/90 |  | WI |  | Material Shortage could increase future bid prices and delay construction completion | A regional cement shortage has begun to impact projects Fall 2014. Suppliers have limited deliveries and contributing factors are a range late ice-out last spring to silt-clogged rivers in the summer to fires and mechanical breakdowns at Midwestern plants. Problems with barge traffic together with congested railroads have more contractors turning to trucks to deliver the supplies they need. It is unclear if the shortage will continue into Spring 2015 construction or if a future shortage could occur. Cement shortage could increase bid prices on future projects. | Construction
Initial |  | I-39/90 |  | WI |  | Real Estate not cleared by Ad Date may delay lets (lets through Calendar 2015) | If a let is delayed due to not having Right of Way cleared, there could be an increased cost in the let due to inflation. 15-20 projects | Right of Way
Initial |  | I-39/90 |  | WI |  | Changes in priorities require adjustments to Construction project start/end dates. | Delay / change in program - Construction Impacts: delay in schedule, cost to advance projects; redesign / repackaging; additional I/E, CCO's for 2020+, changes in items other than inflation. | Organizational
Initial |  | I-39/90 |  | WI |  | Potential of more unexpected subsurface conditions than planned | Encounter unexpected subsurface conditions or poor soils. Additional EBS may be needed if poor soils are incountered or if soils exploration data not fully completed and analyzed. CMT & AECOM to add staff to effectively review geotechnical reports in a timely manner. Will continue to be monitored. | Construction
Initial |  | I-39/90 |  | WI |  | Borrow Material Site | BIC requires a substantial amount of borrow. Available sites are unknown at this time. | Construction
Initial |  | I-39/90 |  | WI |  | Optimized pile lenghts for foundation | Use a pile load test program to optimize foundation design and minimize pile lengths at BIC. | Structure and Geotechnical
Initial |  | I-39/90 |  | WI |  | Alternative Refinement - SB Lane Development | There are 2 sub-options under consideration for how lanes are developed along SB I-39 prior to the SB-WB exit ramp. The options compare whether the two added lanes become the two exit only lanes to WB US 12/18, or if one lane should be added for the exit lane to US 12/18 and one lane should be added for SB I-39 through the core of the interchange. | Design
Initial |  | I-39/90 |  | WI |  | Alternative Refinement - SB-WB Ramp Diverge | There are 2 sub-options under consideration for the SB-WB ramp diverge. The comparison evaluates maintaining the ramp diverge immediately adjacent to the SB lanes of I-39 versus providing a 4-foot buffer between the ramp lanes and SB mainline. | Design
Initial |  | I-39/90 |  | WI |  | Alternative Refinement - NB I-39 Subgrade Construction for Future 3rd Lane (North of Femrite Dr) | There are 2 sub-options under consideration for the construction of the NB I-39 subgrade within the core of the BIC. The comparison evaluates providing the earthwork along the median of NB I-39 for a future third lane through the core of the interchange to Femrite Drive (in preparation for a future improvement not currently programmed) versus only building the subgrade needed for the two lanes being constructed through the core after the lane drop. There is the potential additional subgrade construction would be required north of Femrite Drive to the UPRR. | Design
Initial |  | I-39/90 |  | WI |  | Retaining Wall for Section 4(f) Avoidance in National Environmental Policy Act Review (NEPA) process and documentation | The project currently includes the cost for a retaining wall along Yahara Hills Golf Course for Section 4(f) avoidance in National Environmental Policy Act Review (NEPA) process and documentation. If the city of Madison provides concurrence with the evaluation of potential impacts as “de minimis" the wall would be replaced with grading and a berm. | Environmental
Initial |  | Birmingham Northern Beltline | Green Projects | AL |  | Standard Stormwater Management may not be adequate to ensure protection of watershed and endangered species | Standard Stormwater Management may not be adequate to ensure protection of watershed and endangered species | Environmental
Initial |  | Birmingham Northern Beltline | Green Projects | AL |  | Unknown soil conditions impacting bridge construction | Includes unclassified soils, unforeseen, underground coal or iron mines, and unknown landfill. | Construction
Initial |  | Birmingham Northern Beltline | Green Projects | AL |  | Additional bridges (i.e. more than 1) needed to cross the Cahaba river | Mitigation for Cahaba River society. Cahaba river society is trying to prevent the construction of the BNB. Additional bridges could be let with existing projects and would not require additional schedule. | Design
Initial |  | Birmingham Northern Beltline | Green Projects | AL |  | Unforeseen roadway soil conditions | Additional construction may be required to account for unforeseen landfill or rocks. ALDOT does not incur schedule risks. | Construction
Initial |  | Birmingham Northern Beltline | Green Projects | AL |  | Environmental Mitigation Costs | Unanticipated environmental mitigation costs due to threatened and endangered species, wetland streams, archaeological, community impacts | Environmental
Initial |  | I-74 Quad Cities Corridor Study | Phase 2 | IA |  | Additional Right-of-Way Costs due to Condemnation and/or Appeal | During acquisition of Right-of-Way, property owners may dispute the offer made for their property. This could lead to an increased cost. No impact to the schedule has been identified because of the time between the start of right-of-way acquisition and the start of construction. | Right of Way
Initial |  | I-269 Corridor Project | Project-wide | MS |  | Environmental Re-evaluation and Permitting | Environmental Re-evaluation and Permitting | Environmental
Initial |  | I-269 Corridor Project | Project-wide | MS |  | Erosion Control within existing Right of way acquisition issues | Erosion Control within existing Right of way acquisition issues | Right of Way
Initial |  | I-269 Corridor Project | Section 3 | MS |  | right of way Acquistion | right of way Acquistion | Right of Way
Initial |  | I-269 Corridor Project | Section 1 | MS |  | Utilities relocation | Utilities relocation | Utilities
Initial |  | I-269 Corridor Project | Section 3 | MS |  | Coldwater River Bridge Geotechnical Unknowns | Bridge has to lengthened but unknown about geotechnical, contractor access through swamp. May have to let sep project to build access road and drilled shaft test project. | Structure and Geotechnical
Initial |  | I-269 Corridor Project | Project-wide | MS |  | Creativity from Contractors | Creativity from Contractors | Construction
Initial |  | I-269 Corridor Project | Project-wide | MS |  | Length of Drilled Shafts - Design | Length of Drilled Shafts - Design | Structure and Geotechnical
Initial |  | I-269 Corridor Project | Project-wide | MS |  | Length of Drilled Shafts - Construction | Length of Drilled Shafts - Construction | Construction
Initial |  | I-269 Corridor Project | Section 3 | MS |  | Relocation of electrical transmission line | Relocation of electrical transmission line | Utilities
Initial |  | I-269 Corridor Project | Project-wide | MS |  | Cost of fuel increases | Cost of fuel increases | Management and Funding
Initial |  | I-269 Corridor Project | Section 3 | MS |  | Staging areas for the Coldwater bridge/WRP | Staging areas for the Coldwater bridge/WRP | Construction
Initial |  | I-269 Corridor Project |  | MS |  | Natural disater (hurricane or earthquake) | Natural disater (hurricane or earthquake) | Management and Funding
Initial |  | Cleveland Innerbelt | CCG3,4,5&6 | OH |  | Increased right of way Costs | Increased right of way Costs | Right of Way
Initial |  | SH 99 Grand Parkway, Segment H and I-1 | H & I I-1 int | TX |  | right of way aquisition | Right of Way acquisition by the developer may impact project schedule | Right of Way
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | Assigned staff may not be able to work on the project or delivery on time. | Assigned staff may be reassigned to higher priority projects or transfer to other units. | Organizational
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | Funding is not available in the programmed fiscal year. | Due to State budget constraints, the programmed project may lose funding for a year or more. | Management and Funding
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | Independent specialists not available. | independent specialists such as Registered Forester, Independent Appraiser, Expert Witness not immediately able to work on the project or deliver on time. | Organizational
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | right of way in-house Specialists not available. | RW In-house specialists such as for Utilities, Federal Lands, Excess Lands, Railroads, etc. not able to work on the project or deliver on time. | Organizational
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | Changes in Law. | Federal or State Constitutional or Regulatory requirements change resulting in more cost, work and duration to complete. | Procurement and contracting
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | Parcels to acquire are "unique". | Parcels to be acquired are found to be "unique" such as, special use properties, goodwill, zoning, cut/reface, relocation housing not available, hazardous waste, tribal lands, Government Lands, Railroad Land, etc. Acquisitions of these parcel types require a longer duration. | Right of Way
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | Utility owners not financial solvent. | Utility owner unable to relocate at their expense even if liable to do so. Will lead to protracted negotiations, loan attempts, considerations for CT contractor to relocate and bill owner, etc. These situations take much longer to resolve. | Utilities
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | funding not available to hire specialists. | Independent contractor required for special component to RW acquisition such as a registered forester, but due to funding constraints we are unable to contract them. | Organizational
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | Grantor's past history with the Department. | Grantor's past history with Department suggests protracted negotiations. If we had to go to condemnation previously, a better likelihood exists that it would happen again potentially delaying the project. | Stakeholder
Initial |  | I-215 San Bernardino North Corridor Project (from I-10 to I-210) |  | CA |  | New improvements constructed in proposed right of way. | Property owners construct new improvements within the proposed right of way from the time of the initial Right of Way estimate to the time of acquisition causing an increase in acquisition cost. | Right of Way
Initial |  | Rt. I-295 & 42/I-76 Direct Connection | Projectwide | NJ |  | right of way Acquisition Cost | Accounts for risk associated with critical parcels required for Contract 2. Additional cost includes acquisition, settlement, and administrative. | Right of Way
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Project Public Policy Risk | PUBLIC POLICY: This project is enthusiastically supported by the Governor, Lt. Governor, Secretary of Transportation and General Assembly. | Stakeholder
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Project Public Policy Risk | PUBLIC POLICY: This project is enthusiastically supported by the Governor, Lt. Governor, Secretary of Transportation and General Assembly. | Stakeholder
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Contractor Changes | PERMIT REVISIONS: The Design Build Contractor will have flexibility to revise the design which could result in additional or changed environmental impacts. These changes would require an update/approval of the Environmental Assessment. This brings a risk to contractor schedule and budget | Procurement and contracting
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Contractor Changes | PERMIT REVISIONS: The Design Build Contractor will have flexibility to revise the design which could result in additional or changed environmental impacts. These changes would require an update/approval of the Environmental Assessment. This brings a risk to contractor schedule and budget | Procurement and contracting
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Environmental Permitting | PERMITTING DELAYS: The District is taking a very proactive approach to environmental studies and data collection to expedite DB Contractor permit acquisition. Risk of doing more is taking on inordinate responsibility and opening up to contractor claims | Environmental
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Environmental Permitting | PERMITTING DELAYS: The District is taking a very proactive approach to environmental studies and data collection to expedite DB Contractor permit acquisition. Risk of doing more is taking on inordinate responsibility and opening up to contractor claims | Environmental
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Stakeholder Requirements (USN, VMA, VPA Pilots, Coast Guard, US Customs) | REGULATORY DELAYS: There is extensive marine work in and around the Thimble Shoat channel, a major channel for port and military traffic. Without good coordination and proactive communication, this can lead to to conflicts over channel availability and lead to contractor delays. Construction of a island in the Chesapeak Bay is not routine work and Department of Environmental Quality (DEQ) assessment is a risk. | Stakeholder
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Stakeholder Requirements (USN, VMA, VPA Pilots, Coast Guard, US Customs) | REGULATORY DELAYS: There is extensive marine work in and around the Thimble Shoat channel, a major channel for port and military traffic. Without good coordination and proactive communication, this can lead to to conflicts over channel availability and lead to contractor delays. Construction of a island in the Chesapeak Bay is not routine work and Department of Environmental Quality (DEQ) assessment is a risk. | Stakeholder
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Section 103 Dredge Environmental Permit | DISPOSAL RISK: The handling and disposal of dredge and excavated materials can be costly on this project if ocean disposal is not approved. Time consuming testing for impact of disposed soils is required for the Section 103 permit. Contractor allocation of risk of delay can cause changes or higher bids depending on allocation of risk. | Environmental
Initial |  | Thimble Shoal Parallel Tunnel Project |  | VA |  | Section 103 Dredge Environemntal Permit | DISPOSAL RISK: The handling and disposal of dredge and excavated materials can be costly on this project if ocean disposal is not approved. Time consuming testing for impact of disposed soils is required for the Section 103 permit. Contractor allocation of risk of delay can cause changes or higher bids depending on allocation of risk. | Environmental
Initial |  | US 68/KY80, Lane Between the Lakes, West of Cadiz, KY | 1-180.10 | KY |  | Asbestos, Lawsuite, & Demolition | Asbestos, Lawsuite, & Demolition | Procurement and contracting
Initial |  | US 68/KY80, Lane Between the Lakes, West of Cadiz, KY | 1-180.11 | KY |  | Asbestos, Lawsuite, & Demolition | Asbestos, Lawsuite, & Demolition | Procurement and contracting
Initial |  | US 68/KY80, Lane Between the Lakes, West of Cadiz, KY | 1-180.51 | KY |  | UST, Asbestos, Lawsuite, & Demolition | May cause project delays. | Procurement and contracting
Initial |  | I-94/Edsel Ford Freeway | Phase 1 | MI |  | Damage to Properties | Impacts to existing buildings and parking areas and provide access during construction; pertains to properties geographically in Segment 2, but construction included in Segment 3 | Construction
Initial |  | I-94/Edsel Ford Freeway | Phase 1 | MI |  | Additional right of way for RR in Segment 3 | Additional Right of Way to accommodate temporary tracks; includes cost for both RR in Segment 3 | Right of Way
Initial |  | I-94/Edsel Ford Freeway | Phase 3 | MI |  | Additional right of way for RR in Segment 1 | Additional Right of Way to accommodate temporary tracks | Right of Way
Initial |  | Tri-County Freeway | Projectwide | WI |  | right of way Litigation | Litigation on Real Estate Impacts | Right of Way
Initial |  | Tri-County Freeway | Projectwide | WI |  | Real Estate Cost Contingency | Additional Real Estate costs due to market/schedule or other reasons | Right of Way
Initial |  | I-5 North Coast Corridor Project, San Diego County | Package 1 | CA |  | Right of Way -1 Manchester Parcels | Possession of Manchester Parcels. Strawberry fields. 2 parcels-don't need the second parcel right away, moved into Package 2. | Right of Way
Initial |  | I-5 North Coast Corridor Project, San Diego County | Package 1 | CA |  | Utilities conflicts -1 Santa Fe Water Line | If design or permits are delayed because of utility conflicts it will cause a delay in the overall schedule | Utilities
Initial |  | I-5 North Coast Corridor Project, San Diego County | Projectwide | CA |  | Right of Way -2 Manchester Gas Station | Impacting a driveway due to a gas station. Removing one of the driveways. Creating a new access road. Reconfiguration will allow to put another driveway in. May need to relocate water valve across the street. Additional delay to schedule possible. | Right of Way
Initial |  | I-5 North Coast Corridor Project, San Diego County | Projectwide | CA |  | Utilities conflicts -2 Protecting Escondido Sewer Line Summer 2015 | First order of work. Lining (or protection in place) needs to be done before heavy loads can be placed on top. Lining during high flow (after Aug) reduces period of shutdown to 2-3 hours. | Utilities
Initial |  | I-5 North Coast Corridor Project, San Diego County | Package 1 | CA |  | Utilities relocation -5 JPA Recycled Water Line, Solana Beach Sewer Line | Will likely have to replace the entire line. Has to be done prior to construction. No monetary threat, just a schedule threat. | Utilities
Initial |  | Zoo Interchange (I-94/I-894/US-45) | Global | WI |  | Increased excavation costs | Given level of design, risk of excavation below subgrade that is currently not accounted for in the estimate. | Structure and Geotechnical
Initial |  | Zoo Interchange (I-94/I-894/US-45) | Global | WI |  | Right of Way Acquisition is more costly than expected | Due to County Owned Facilities, state fair, Milwaukee County Zoo, and Dept of Public Works. Relocation of Zoo maintenance facility ($13 million @ 20%), Dept Public Works Maint Facility, Green houses for County, Salt Dome and park and ride at watertown park interchange (17 million at 20%), Zoo Parking (10 million @ 50% prob), State Fair Parking (5 million @ 50%) | Right of Way
Initial |  | Zoo Interchange (I-94/I-894/US-45) | Global | WI |  | Opportunity Design Change for Watertown Plank Road Interchange | Possibility of a design change to reduce the cost of the interchange to the Watertown plank road based on comments from the Interstate Access Justification Report. Save on ROW and structures. Saving 2 u ramp structures. | Design
Initial |  | Zoo Interchange (I-94/I-894/US-45) | Global | WI |  | Higher real estate cost due to development, annexation, rezoning | Univ. of Wisc Milwaukee and Eaton Reseach Park. UWM plan to develop land into engineering campus. Eaton Research Park plans to develop land both impacted by loop ramp. Concern is that we make a parcel undevelopable. Impact two park and ride lots that need to be replaced. Park and ride lots at west side of US 45 on the Watertown plank road interchange | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.01 | Environmental combined documentation / re-evaluation | This risk concerns for PD&E documentation and not permitting that may potentially delay advertising. The Project Team has made progress on this and is no longer a concern. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.02 | Need for Environmental re-evaluation | Need for Environmental re-evaluation | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.03 | Change in environmental regulations | Change in environmental regulations | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.04 | Delay to wetland permits (or challenge to permit, such as from public opposition) | The Project Team is looking for ACE approval for a request relating to wetland permit but this should not be delaying NTP or advertising- the likelihood of approval is about 90 percent based on prior experience. The risk is also related to the permit needed for the airport- BOCC. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.05 | New Environmental permits or new information required | New Environmental permits or new information required | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.06 | Impacts to cultural/ archeological/ historic sites | Potential historic location is Speedway. Historic entrance on Ulmerton Road is closed in the 256995-3 project. Section 106 has been completed. No other areas of concern. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.07 | Endangered species present | Endangered species present | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.08 | Buried man-made objects and unidentified hazardous materials | Buried debris, some of which was contaminated, was encountered during construction of 256995-2 floodplain compensation site east of the race track. The Project Team has established enough borings and will ensure the contractor has the information related to geotech. Near the airport (previously a military base), there has been findings (man-made, military equipment for example) near the remote parking but work is not being done there. There is a restrictive agreement on working in that area and the language is in the RFP. This project is in the area that is previously being disturbed by the airport so nothing is anticipated here. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.09 | Encountering contaminated material | One location may be north of 118th/ Speedway. There is a site adjacent to the limited access ROW and the project team will look to assess any potential impacts. The contamination related to debris has been addressed and the condition has been assessed with borings, depth of foundations reviewed. For the concern of general contamination, the risk has been reduced due to borings already done. If contamination is found, the contractor can work in other areas to avoid delays. Other common issues can include contaminated soil and groundwater. There will be contractor(s) brought in to address contamination issues (such as dewatering). This is a separate contract and fund is set aside in case this occurs. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.11 | Negative community impacts cause delays | Negative community impacts cause delays | Stakeholder
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.12 | Noise walls required | Noise walls required | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.13 | Additional wetland mitigation required | Additional wetland mitigation required | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.01 | Changes in design | Design may change depending on conflicts between FGT and drainage. Another change may arise from ACT. Not anticipating design change prior to RFP. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.02 | Change in alignment (vertical or horizontal) | Design may change depending on conflicts between FGT and drainage. Another change may arise from ACT. Not anticipating design change prior to RFP. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.03 | Design-builder innovations | DB Innovations – a combination of a number of potential design efficiencies and construction sequencing. On larger projects such as this one, the Project Team has seen bids come in and average 17 percent under the engineers estimate. The project team assumes this is due to economies of scale, uniform designs across segments (since no restrictions), etc. Cost savings reflect 10-20 percent of construction cost; schedule impact is accounted for within incentive ($8M programmed but in the base- $40k a day for 200 days). | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.04 | Design Build delivery incentive | Schedule impact from DB innovations is accounted for within incentive ($8M programmed but not in the base- $40k a day for 200 days). The cost of the incentive is not quantified since the contractor will likely bid $8 million less and achieve the schedule savings so the net cost impact is zero. Opening early may have an impact to toll revenue and financing; however these impacts are not captured and are not within the scope of the risk assessment. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.05 | Additional exit required | Additional exit required | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.06 | Need for design exceptions / variations | There are variations required for the current design (will be part of concept plan); the risk concerns ATC for example; lane width and shoulder width exceptions approval, delay, is not a risk. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.08 | Changes in Environmental standards | Mitigation of this risk requires on-going coordination with maintenance, drainage, etc. Not an issue. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.13 | Replacement of fiber optics utilities | The LRE has the cost of fiber optics conduits on one side of the roadway and not the other. The risk concerns the need to replace the fiber optic cable on the other side of the roadway. The risk concerns replacement or relocation- action item is to assess feasibility. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.14 | Coordination of tolls | Tolling agreement is not an issue. | Traffic
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.16 | Delay in tolling operations (e.g., due to delay in communications being operable) | Prior to commissioning of the tolling facility there are a number operational tests that need to be conducted. TEC has indicated that they should be able to complete in 21 days per facility (there are five movements- add 100 days to TEC activity in schedule); add cost on TBX equipment. No delay quantified. | Traffic
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.02 | SR 686 - change in design mix of structure vs. retained fill near 43rd and 118th | Design innovations relating to reduction in materials are captured in DES.03. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.03 | Change in configuration of one or more interchange | Design innovations relating to reduction in materials are captured in DES.03. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.04 | Change in mix of replaced vs. widened structures | The 118th Ave at I-275 bridges have not been assessed like the others and there may be a risk of having to replace them- the Project Team is fairly confident in the feasibility of the widening. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.05 | Design changes on bridge or overpass | Design innovations relating post advertisement are captured in DES.03. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.06 | Shorten flyover structure from CR 611 to SR 686 | Design innovations relating post advertisement are captured in DES.03. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.08 | Changes to structural design | There may be some minor changes in structural design criteria but nothing major. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.09 | Need to widen / replace additional bridges | Need to widen / replace additional bridges | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.11 | Encounter unanticipated sinkholes or difficult foundation construction | Encounter unanticipated sinkholes or difficult foundation construction | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.12 | Unforeseen foundation issues | The Project Team has encountered debris near US 19 in the median- will need to excavate, use special equipment for removal, drive different piles, etc. No schedule impact since the contractor can always work in different locations. | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.13 | Subsurface conditions related to unsuitable soils | Subsurface conditions related to unsuitable soils | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.16 | Change in type or length of deep foundations (piles/shafts) to reflect field conditions | There is a risk; however it is small as all borings already been conducted. The impact is minimal as the contractor can work in other areas to minimize delays. | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.01 | Delays in utility agreements | Utility owners include Duke Transmission, Duke Distribution, City of Largo, City of Pinellas Park, etc. and negotiation is on-going. In terms of schedule, project team plans to have agreements prior to award; the latest agreement is needed to be in place prior to last round of ATCs (August 1, 2016). | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.02 | Utility betterment requests | The Project will not be responsible for the cost of betterment requests- not a risk here. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.03 | Delays in utility relocation | For relocations planning prior to construction the project team will revise RFP to reflect the relocation status/ how much is completed and what the contractor should expect as far as remaining relocation goes. The RFP has requirements on coordination (coordination with utility owners, schedule planning to work efficiently, material procurement, and designing around the relocation work, etc.) and risk concerns unanticipated contractor delays during construction. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.04 | Base cost for utility relocation | In terms of programmed cost, there is $25M ($20M for FGT and $5M for Duke). The RISK ASSESSMENT estimate at the start of the workshop has $20M ($15M for FGT and $4M for Duke Transmission, Duke Distribution, City of Largo, City of Pinellas Park, etc.) and the potentially reimbursable is $15M - other non reimbursable is not included and will be funded by locals for their relocations.. The base cost should be $15M plus or minus 5 percent. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.05 | Additional cost for utility relocation | Additional cost for utility relocation | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.06 | work windows | The risk concerns seasonal or time of day restrictions outside of storm events. FGT and Duke both have these type of work windows but the construction schedule should allow for the work. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.07 | Duke Energy does not relocated utilities in time | Duke Energy Transmission located in easements; compensable relocations/adjustments; crossings at: new alignment flyovers on north side of 118th Avenue, new alignment at 126th Avenue. Currently the cost of the relocation is not anticipated and the schedule impact is captured under risk on utility relocation delay risk item. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.08 | Uncertainty in cost to raise Duke T-lines (who pays at 126th) | This has been resolved and the cost is in the base estimate. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.09 | Required unplanned Duke Energy T-line shut-down | The Project Team has addressed potential outages with construction sequencing. No longer a risk. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.10 | Other private utilities (Verizon, etc.) not relocated in time | The risk is captured under general utility relocation delay risk item. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.11 | FGT utility coordination issues | The Project Team is negotiating with FGT for relocation of a gas transmission line within existing ROW. The potential additional cost for ROW purchase of $4M is within the base cost. ROW impact accounts for having to acquire 24-ft wide area for FGT. This takes about 2 years and will start Jan 2016. The likelihood of delays related to FGT coordination is low as there are only two parcels impacted. Additionally, FGT is looking to reduce the footprint. The relocation should only take about two months since FGT is expected to be working on permits during ROW acquisition. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.12 | Local jurisdictions/ municipalities get contractor to relocate utilities | The project is not responsible for cost on utility relocation and the plan moving forward is to have local jurisdictions/ municipalities get contractor to relocate utilities. No longer a risk. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.14 | Issues with utilities complying with Buy America | Issues with utilities complying with Buy America | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.15 | Encounter (and possibly damage) unknown utilities during construction | Design builder is responsible to coordinate with utility owners but it may be possible that the owners do not provide the most updated/ accurate information. Ultimately FDOT will not be responsible for the cost of relocation but the amount will be reflected as a project cost (cost will be reimbursed back to general funds). The cost impact can be mitigated with the owners paying the contractor directly. The bigger concern is unknowns such as out of service lines. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | RRD.01 | Delay in railroad agreements | Delay in railroad agreements | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.01 | Delay in right of way document internal approval process | Delay in right of way document internal approval process | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.02 | Design changes impact right of way needs | Design changes impact right of way needs | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.03 | Delays in right of way acquisition | There is one parcel that may be a potential concern but this will not stop construction. Anticipated to be resolved prior to the DB Design, which is about 6 months into the DB contract. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.04 | Additional right of way required for utility relocations | Additional right of way required for utility relocations | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.05 | Additional right of way for ATC | Additional right of way for ATC | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.06 | Potential for lawsuits related to right of way | The Project Team is not anticipating any lawsuits. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.07 | Elimination of three parcels | Most of the Right of Way has been acquired and not expecting higher cost. Depending on potential changes in design, there may be a chance of eliminating three parcels. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.08 | change in access | If the three parcels (ROW.07) are not impacted then there may be reduction in impacts to business- minor though. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.11 | Delay in Board of County Commissioners (BOCC) approval to locate ponds at airport | Delay in Board of County Commissioners (BOCC) approval to locate ponds at airport | Stakeholder
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.12 | Need for additional right of way at gantry | All the locations are identified and they fit in the footprint. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.13 | right of way Cost increases at US 19 due to increased compensation | Potential cost increase relates to court decision on cemetery property and additional from temporary construction easement (TCE) - the base cost has been adjusted for $9M to account for this risk item. In terms of schedule, the Project Team expects this to be resolved quickly- no delays. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.14 | Existing leases | At this point, Terri Cummins horse farm- lease has not been renewed. Showtime Speedway & Dragstrip- has been designed around. Sunshine Motocross-lease has not been renewed. No delays expected. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.01 | Staging area limitations (opportunity to use raceway property if don't renew lease) | CP2 Staging area limitations - mostly covered under base uncertainty range for mobilization, except for possibility of a separate >5-acre site. This is been resolved with additional space available within ROW acquired. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.02 | Different site conditions | This risk accounts for issues beyond potential geotechnical issues (captured under STG.12 and STG.15). The DB contractor is expected to handle the conditions with design solutions. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.03 | Weather related interruptions to construction | Routine weather impacts are handled within the contract language and are not a risk. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.04 | Nonconforming work results in schedule delay | This issue will not likely to have significant schedule impact. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.05 | Change orders | For design-bid-build, average overruns (which includes change orders and incentives) across the state is about seven percent. For design-build (which Phase 1 is) it is about three percent. For this project, three percent of construction is $12M and this includes both change orders and incentives in FDOT’s program accounting. There is an $8M incentive programmed for design-build innovations but this is not included in the risk assessment because realizing contractor will include this in their bid to be competitive, the net effect is therefore zero. Accounting Removing for the $8M incentive to reflect the net effect, the risk addresses the remaining $4M. In terms of schedule, no delay is expected. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.06 | Change in design during construction | This risk is captured under CNS.05 change order item. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.07 | Other work-window restrictions (not captured separately) | Risk related to utility relocation and weather has been captured. In terms of special events, no significant impact expected. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.08 | Connections to other projects | Nothing scheduled for FDOT and the Project Team is not aware of other local projects. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.09 | Interference from other projects | On-going coordination with Ulmerton Road (256995-3) construction will be addressed in the RFP. The anticipated completion in March 2017 (not accounting for weather days or other delays). | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.10 | Ulmerton Road project not completed in time | The risks related to Ulmerton Road are addressed. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.11 | Construction contract duration uncertainty | For Phase 2: Duration could range 1200 to 1400 calendar days; Phase 3: duration could range 800 to 1000 calendar days. The schedule has been reviewed again and the Project Team is comfortable with the base estimate. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.12 | Change in construction sequencing / phasing (improved or slower relative to base, redundant w PD16?) | The opportunity of combining contracts is already implemented as a base. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.15 | Can't reuse excavated materials from ponds for embankment | Geotech reports/ assessments will be provided to the contractor. The base assumes excavation; the opportunity to reuse materials for embankments captured under design innovations. | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.16 | Poor contractor performance | Poor contractor performance | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.17 | Compensable weather delays | This risk accounts for weather delays for which the contractor can be compensated. An example would be a severe weather event where the contractor is required to shut down and secure the work site in anticipation of a storm. There is no monetary compensation provided to contractors for rain days, therefore this risk does not account for rain days. In terms of schedule, the likelihood is about 50 percent for 1-2 weeks of delay over four years of the contract. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.19 | Different work windows for viaduct construction (more or less restrictive) | The risk concerns lane closure and ability to do so. There should be limitations within the RFP- the language now is restrictive and the issues are unlikely to be a risk. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.20 | Issues maintaining utility connections to airport | Issues maintaining utility connections to airport | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.21 | Injunction during construction | The project runs through commercial properties and the Project Team does not think this is a risk anymore. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.22 | Significant construction accident (or accumulation) | This is a risk but the likelihood is low. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.23 | Difficulty obtaining any specialty equipment/ material | The risk concerns long lead items, equipment, materials but nothing extraordinary expected. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.01 | Management decisions/ priorities delay the project | The project has been funded and moving forward. No risk. | Management and Funding
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.02 | Change in critical staffing during the project | Staffing is not a real concerns and availability of resources has been mitigated with staggering of projects. | Organizational
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.03 | Inexperienced workforce / inadequate staff / resource availability | Not a concern here- should be able to make adjustments to stay on schedule. | Organizational
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.04 | Unplanned work that must be accommodated, change order | Captured under change order risks. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.05 | Additional maintenance items included in construction contract | Captured under change order risks. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.06 | Funding delay (State or County, such as Pennies for Pinellas) | Funding delay (State or County, such as Pennies for Pinellas) | Management and Funding
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.07 | Advanced funding (from other projects) allows acceleration (mutually exclusive with other funding risks?) | The opportunity to accelerate based on DB delivery may be limited. Not a risk here. | Management and Funding
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.08 | Pressure to deliver project on an accelerated schedule | The opportunity to accelerate based on DB delivery may be limited. Not a risk here. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.01 | Delays in Environmental Process | For the Environmental process for Phase 2, no salt water associated with the project in the area so not a big issue here. For Phase 3, there is a bigger concern as it involves coordination with national fisheries service (NFS), Coast Guard at big island gap due to bridge widening. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.02 | Change in environmental regulations | The change in regulations is likely to be stormwater related. This means that the impact on the project will be minimal. Impact may be on pond size (ROW) and the risk accounts for ROW cost. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.03 | Impacts to cultural/ archeological/ historic sites | There is no anticipated major impact since the area is developed. Coordination with SHPO may be needed. No impact on Phase 3 since working within existing ROW | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.04 | Protected/ Endangered species present | The anticipated impact is minimal but there is still a chance for projects so far out into the future. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.05 | Buried man-made objects unidentified hazardous materials | There may be some impacts on Phase 2 given the findings in P1; impact on Phase 3 has not been fully assessed. The risk of finding something exists but low. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.06 | Addition of sound walls | The base estimate does not have any sound wall for Phase 2 as it is primarily commercial- only one apartment complex identified with minimal noise receptors | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.07 | New Environmental permits or new information required | New Environmental permits or new information required | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ENV.08 | Primary and secondary wetlands impacts - additional mitigation required | Wetland impact is expected to be low. There may be some infills. The base cost estimate on Phase 2 should be sufficient. | Environmental
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.01 | Changes in design | In general there can be improvements in safety that may impact design. Quantification is per phase. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.02 | Change in alignment (vertical or horizontal) | Captured under change in design. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.03 | Need for design exceptions / variations | Captured under change in design. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.04 | Design review delays project schedule | Review this risk item when the projects get closer to design. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.05 | Changes in design | Review this risk item when the projects get closer to design. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.07 | Design schedule constraints | Review this risk items when the projects get closer to design. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.08 | Design-builder innovations | Currently not assumed to be DB projects. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | DES.09 | Pavement replacement versus widening | Phase 3 has concrete pavement. The concrete pavement has a 30-year lifecycle (it was completed five years ago) so there may be need to be a full reconstruction by the time the Phase 3 project occurs. Quantification is based on $75 per sq. yard for 7,040 sq. yard per lane mile. The per lane mile cost is about $0.5M just for the concrete. Another $0.5M accounts for subgrade, drainage, MOT, MOB, etc. for a total of $1.0 million per lane mile. Total is about 60 lane miles. Schedule impact accounts for both bridge (STG.03) and pavement replacement. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.01 | Change in configuration of one or more interchange | Currently the assumption of TBX connection is not anticipated to change. For Phase 3, change is not expected. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.02 | Change in mix of replaced vs. widened structures | The need to replace structures will be triggered by state of good repair. For Phase 3, the existing structures will be nearly 60 years old at the time of the project. The condition may be good enough to be maintained to 100 years. For a rough estimate, the cost will be four times as much as the base cost estimate for bridges on Phase 3, because of replacement of four lanes versus widening of one lane, plus MOT cost. Potential schedule impact is captured under pavement replacement risk item (DES.09). | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.03 | Design changes on bridge or overpass | There may be a change under Phase 2- will monitor as the project gets closer to design. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.04 | Changes to structural design criteria | There may be a change under Phase 2- will monitor as the project gets closer to design. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.06 | Encountering sinkholes | Encountering sinkholes | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.07 | Foundation issues | The Project Team has already conducted a number of borings for Phase 2 (except for 256998-2); no major concerns. | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.08 | Unsuitable soils/ muck | Unsuitable soils/ muck | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | STG.09 | Temporary sheet pile walls | For Phase 2, temporary sheet piles (for approaches to bridges, utility, drainage, protection of parcels, etc.) have not been included as design is not far enough ahead. The need for Phase 3 may not be a risk as the work is roadway widening. | Structure and Geotechnical
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.01 | Delays in utility agreements | Known utilities in Phase 2 include fiber optics, telephone, Duke transmission; FGT in Phase 3 will not be impacted by areas of inside widening. No foreseeable issues at this point. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.03 | Delays in utility relocation | For Phase 2, fiber optics and telephone lines relocation should occur prior to DBB construction and there should not be issues if designing around the trunk lines. For Phase 3, there may be issues with utilities near bridges. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.04 | Additional cost for utility relocation | For Phase 2, cost for relocations will depend upon whether they are compensable. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.05 | Additional cost for utility relocation | For Phase 3, everything within limited access ROW is most likely to be compensable. There's potential conflict near St. Pete viaduct (segment of I-275 between 175 and 375). Quantifications are based on 5 instances of $200k-$400k for instance. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.06 | Unexpected utility impacts during construction | There is a potential for this to happen on any project and this applies to both phases. Cost ranges from $10k-$40k per instance. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.07 | Unexpected utility impacts during construction | There's a potential for this to happen on any project and this applies to both phases. Cost ranges from $10k-$40k per instance. | Utilities
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.08 | work windows | This is not a concern to the projects. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | UTL.09 | Changes in roadway design | The risk concerning utility relocation is captured under other utility relocation risk items. | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | RRD.01 | Delay in railroad agreements | For Phase 3, there is a bridge going over CSX railroad. The agreements there need to be worked out as project progresses. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.01 | Delay in right of way document internal approval process | The standard for Right of Way process is two years, which is assumed in the current schedule. The risk will be tracked as projects move on. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.02 | Delays in right of way acquisition | The standard for Right of Way process is two years, which is assumed in the current schedule. The risk will be tracked as projects move on. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.03 | Design changes | Design changes | Design
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.04 | Right of way cost higher than anticipated | The risk of higher than expected costs is captured under additional Right of Way required. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.05 | Additional right of way required | For Phase 2 256998-1 project, all the Right of Way has been acquired. For Phase 2 256998-2, there is one parcel needed for a pond that is not in the base estimate. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.06 | Additional right of way required | For Phase 3, there may be an opportunity of reduce due to design refinements. The $23M in the base cost is based on a concept including auxiliary land and the current concept does not. Range should be around $15M-$20M. | Right of Way
Initial |  | Pinellas County Gateway Expressway Project |  | FL | ROW.07 | Potential for lawsuits related to right of way | The parcels being impacted have not been identified and the risk will be tracked moving forward. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.01 | Different site conditions | There should not be any issues on Phase 3 since widening on existing ROW. The work on Phase 2 is on fairly developed land so the risk is low. The risk should be revisited when more geotechnical investigation is conducted. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.02 | Compensable weather delays | This risk accounts for weather delays for which the contractor can be compensated. An example would be a severe weather event where the contractor is required to shut down and secure the work site in anticipation of a storm. There is no monetary compensation provided to contractors for rain days, therefore this risk does not account for rain days. (Full impact applies to each Phase). | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.03 | Nonconforming work results in schedule delay | Potential delays can be captured under the variations in construction durations. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.04 | Change orders | For DBB, average overruns (which includes change orders and incentives) across the state is about seven percent. For this project, seven percent of construction is $5M for Phase 2. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.05 | Change orders | For DBB, average overruns (which includes change orders and incentives) across the state is about seven percent. For this project, seven percent of construction is $4M for Phase 3. | Procurement and contracting
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.06 | Work windows | Construction variability should capture the risk of work windows. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.07 | Interference from other projects | Schedule of potentially interfering projects is not well-defined at this stage. Will refine as projects move forward. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | CNS.08 | Construction contract duration uncertainty | For Phase 2: Duration could range 1200 to 1400 calendar days; Phase 3: duration could range 800 to 1000 calendar days. Will refine as projects move forward. | Construction
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.01 | Management decisions priorities delay the project | This can be an issue as project priorities can change. Will continue monitoring the risk. Note if Operationally Independent and Non-Concurrent Construction (OINCC) applies there will be no project phasing. | Management and Funding
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.02 | Change in critical staffing during the project | This risk will be tracked as project progresses. | Organizational
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.03 | Staff/ resource availability | This risk will be tracked as project progresses. | Organizational
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.04 | Funding issues (availability, delays, etc.) | The project is currently not funded. Future funding may an issue as project priorities can change. Will continue monitoring the risk. Note if Operationally Independent and Non-Concurrent Construction (OINCC) applies there will be no project phasing. | Management and Funding
Initial |  | Pinellas County Gateway Expressway Project |  | FL | MGT.05 | Pressure to deliver project on an accelerated schedule | The project is currently not funded. Future funding may an issue as project priorities can change. Will continue monitoring the risk. Note if Operationally Independent and Non-Concurrent Construction (OINCC) applies there will be no project phasing. | Construction
Initial |  | I-395 Reconstruction |  | FL | ENV.01 | Environmental re-evaluation delays | Plan to submit to FHWA by the end of Dec and they have a 30 day period for review and need to be completed by April. Targeted to be completed by April 2015. Also potential delays for SHPO approval of design near historical properties. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.02 | Environmental regulations change | Don't foresee any regulation that would affect the project. Been coordinating with agencies and are not aware of any changes. Should not be a concern for the next year. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.04 | Impacts to species/ endangered species present | Need to acquire permits for canal work. Not an issue for this project. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.05 | Environmental Permits or agency actions delayed or take longer than expected | Need to acquired permits from several agencies (USACE 404, Coast Guards, SFWMD ERP and water use. The ERP permits will be acquired before letting. Coast Guard permits are only for MDX. For 395 have already received a water permits and have already started coordination with USACE. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.06 | Delays in preparation of environmental permit package | Delays in preparation of environmental permit package | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.07 | New Environmental permits or new information required | Already aware of the permits needed or need to be modify. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.08 | Environmental Permitting issues related to work near Canal | Standard previsions are assumed, and have already obtained original permits from Coast Guard. Permits will be procured by the contractor. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.09 | Coordination with stakeholder | Already started coordination with them. Don't foresee any problems. | Stakeholder
Initial |  | I-395 Reconstruction |  | FL | ENV.10 | Coordination with water management agencies | Have started coordination with water Miami-Dade Water. Don't foresee any issues on this project. | Stakeholder
Initial |  | I-395 Reconstruction |  | FL | ENV.11 | Unanticipated cultural or archaeological findings | Potential concern around the river on the MDX segment. Current Base Cost variability already accounts for any cost impact. Low probability of finding cultural or archaeological items: 1- Pre construction whether or not testing will be required. 2- In construction could potentially find something that could impact the project. For the first item working on a waiver with FHWA for preconstruction testing if waiver is not received the risk is capture in reevaluation. For the second item, work will need to stop until the assessment is done. Contractor may need to move around until the assessment is done and this will be put in a note in the RFP. The probability of delay is low as the contractor may be able to work on other areas of the project should something be encountered. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.12 | Impact on historic properties | MDX has been coordinating with locals to resolve any issue on historical properties. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.13 | Section 4(f) resources affected, National Environmental Policy Act Review (NEPA) | National Environmental Policy Act Review (NEPA) process and documentation | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.14 | Contaminated materials present site investigation required | Already included in the Base Cost estimate. In construction, if it's undefined, then it is DOT responsibility. The cost is separately funded and is not part of the project cost. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.15 | Buried man-made objects unidentified hazardous materials found in construction | Already captured in the previous risk item. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.16 | Determination of impacts to wetlands | No wetland impacts on 395, and no impact on MDX. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.17 | Development of detailed wetland mitigation plan | Development of detailed wetland mitigation plan | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.18 | Additional wetlands mitigation area needed | Additional wetlands mitigation area needed | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.19 | Poor erosion control measures | Poor erosion control measures | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | ENV.20 | Noise mitigation during construction | This is an urban area surrounded by cultural site and hospital and high rise residential area. Need coordination with the city of Miami for getting work permits. Methods will need to be addressed early in the design. Potential for schedule delay when complains are received. | Environmental
Initial |  | I-395 Reconstruction |  | FL | STG.11 | Vibration during construction | Studies conducted to mitigate risks of vibration during construction, and specifications are reflected in RFP. However, still some risks near eye doctor office and several historic properties. Potential delays and costs if complaints or if additional time required for re-design | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | ENV.21 | Additional sound walls required due to new development | The risk that FHWA would not accept the current plan is very small. Low probability that additional sound walls would be required. Very low likelihood. A single section could cost $1.5 million. | Environmental
Initial |  | I-395 Reconstruction |  | FL | ENV.22 | Transfer of Environmental Permitting from DB to Department | Transfer of Environmental Permitting from DB to Department | Environmental
Initial |  | I-395 Reconstruction |  | FL | UTL.01 | Delays in Utility agreements | Design plan was changed because of Drainage. Don't foresee any problem in the second round of agreements with Utilities. Have an agreement already with FPL. Anticipate having an agreement with Miami Dade water around March. MDX has a master agreement with FPL, and anticipate a need for agreement with Miami Dade water. Contractor is responsible for getting the agreement and coordination with utilities. | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.02 | Design changes | Current concept is open for design changes. Changes within the current concept could result in increase in UTL costs. | Design
Initial |  | I-395 Reconstruction |  | FL | UTL.02 | Design changes | With current changes in design, utility impact could be lower that what is in the base cost. | Design
Initial |  | I-395 Reconstruction |  | FL | UTL.03 | Utility relocation may not happen on time | General risk related to potential delay in utility relocation could be due to conflict at the bridge foundation. | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.03 | Utility relocation may not happen on time | General risk related to potential delay in utility relocation. Relocation of FPL, and MD water. | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.04 | Additional cost for utility relocation | For I-395, utility cost is conservative and have captured opportunities in other risk items. For 836, this risk is captured in UTL.08. | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.12 | A recently identified utility Distribution line may be in conflict with construction. | A recently identified utility Distribution line may be in conflict with construction. | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.05 | Utility cost may be reimbursable by the project | Utility cost may be reimbursable by the project | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.06 | Finding new utilities during construction | This is an old part of town. There is always a chance that records are not up to date. Will mostly have a schedule impact | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.07 | Differing conditions at utility sites | Will probably have a schedule impact. Already captured in UTL.03 | Construction
Initial |  | I-395 Reconstruction |  | FL | UTL.08 | Utility conflicts on arterials | Utility conflicts on arterials | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.08 | Utility conflicts on arterials | Utility conflicts on arterials | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.09 | Utility relocation cost reduction opportunity | Captured in previous risk items. | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.10 | Gas Transmission Line conflicts | On MDX the ramp connecting to I-95 crosses a gas line and an MSE wall will need to be moved, which is currently on top of gas line, to a new location also on top of the gas line. May require changing design to bridge and additional time in coordination. FDOT and FGT have agreed upon procedures and need to determine if it will apply to MDX for this project. Maybe able to reduce a taper to design a solution that would eliminate this potential issue | Utilities
Initial |  | I-395 Reconstruction |  | FL | UTL.11 | Avoid disruptions / vibrations | The foundation pile driving could impact old utilities that could impact project schedule. This risk can be mitigated in the RFP by requiring contractor to protect utilities. | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | STG.01 | Changing geotechnical conditions (due to new information) | On 836 have completed a lot of boring and haven't encountered any special Geotech issue, same applies to 395. A chance of encountering issues is minimal and captured in the Base uncertainty. | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | STG.02 | Design changes on Bridge or Overpass (Pre-NTP) | On 395 design has already been redefined to mitigate this risk Don't anticipate any changes to the design. | Design
Initial |  | I-395 Reconstruction |  | FL | STG.05 | Risk related to uncertainty of the condition of the existing MacArthur structure to be widened | Risk quantified in the 2012 risk assessment. The scope has been reduced in the new design. The risk still exists however the probability is reduced in the 2014 risk assessment. | Design
Initial |  | I-395 Reconstruction |  | FL | STG.05 | Risk associated with widening existing bridges on 836 | Potential for unforeseen complications that could complicate bridge widening. 1% of the base cost. | Design
Initial |  | I-395 Reconstruction |  | FL | STG.03 | Cost Savings Opportunity for Redecking bridges | Doesn't apply on 395 because its a new alignment. For 836 doesn't apply because its widening and no major redecking. | Design
Initial |  | I-395 Reconstruction |  | FL | STG.04 | Changes in Structure and Embankment | RFP will be descriptive on what can be embankment and what can be bridge structure. There is commitment on the EIS for 395 on the minimum span requirement. | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | STG.05 | Subgrade Issues | Subgrade Issues | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | STG.06 | Changing Geotechnical Conditions (Due to New Information) Drainage related | Discussed in previous risk item. | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | STG.07 | Pavement Spec changes Legal load issues | Pavement design will prescriptive in the RFP and is covered in the base cost. | Procurement and contracting
Initial |  | I-395 Reconstruction |  | FL | STG.08 | Geotechnical surveys late | Survey has already been completed for both projects. | Structure and Geotechnical
Initial |  | I-395 Reconstruction |  | FL | DES.01 | Changes in alignment | Concept are well defined don't foresee any changes in alignment on all projects. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.02 | Changes in profile | Concept are well defined don't foresee any changes in profile. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.04 | Need for design exceptions | Exception on existing conditions still needs FHWA approval and central office. PD&E has already been approved so central office is already familiar with the project. On 395 it took about 3 months to get approval from central office. MDX is using the same format use on I-395. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.06 | Change in design during DB Contract | This risk is transferred to the contractor if he is initiating the changes. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.07 | Impacts of other environmental studies in the area on this project | Impacts of other environmental studies in the area on this project | Construction
Initial |  | I-395 Reconstruction |  | FL | DES.08 | Pedestrian accommodations | On I-395 Design plans already include pedestrian accommodations. | Traffic
Initial |  | I-395 Reconstruction |  | FL | DES.10 | Obtaining design approvals from local agency takes longer than expected | Still waiting for approval from MDT. If they change concepts on 395 could impact the project after DB. FHWA can have full oversight after DB. On previous projects FHWA has not send comments on Designs. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.11 | Design changes impact construction costs and schedule | Design changes impact construction costs and schedule | Design
Initial |  | I-395 Reconstruction |  | FL | DES.13 | Failure to obtain easement from MDT due to design change | Currently working on getting agreement on the concept design, very close on getting final approval from MDT. This will be obtained prior to advertising. If changes are made during construction the DB builder will be responsible for obtaining easement but should not impact the critical path of the project. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.14 | Flaw in design is discovered during construction | Not an issue on this project because it is a design build project. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.16 | Short conceptual design duration to develop the RFP, impact RFP completeness and response risks | Not an issue conceptual design is complete. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.17 | FHWA approval delays for design | Have built FHWA review time for design into the base schedule. Not a risk. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.19 | Design-Builder innovations | This risk was discussed in 2012 risk assessment. D/B Team can implement innovative design and construction methods. Potential to reduce profile on 395 and potential to shorten the taper. There will be an incentive of $7 million offered to accelerate the project which could result in 3 to 6 months schedule reduction. | Construction
Initial |  | I-395 Reconstruction |  | FL | DES.20 | Needs Approvals for exceptions and variations | Needs Approvals for exceptions and variations | Design
Initial |  | I-395 Reconstruction |  | FL | DES.21 | Possibility of more efficient paving design | Possibility of more efficient paving design | Design
Initial |  | I-395 Reconstruction |  | FL | DES.22 | Park-and-ride configuration not determined | No park and ride lots on the project. Not a risk. | Design
Initial |  | I-395 Reconstruction |  | FL | DES.23 | Park & Ride lots in inappropriate location | No park and ride lots on the project. Not a risk. | Design
Initial |  | I-395 Reconstruction |  | FL | ROW.01 | Delay in right of way identification | That is not a risk on either project. ROW needs have been identified including easement. | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.01 | Right-of-way acquisition takes longer than expected | 836 - Potential delay in acquisition of government properties. Could increase the base schedule from 3 to 6 months. Monetary impact is captured in the base cost variation. | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.02 | Higher real estate cost due to development, annexation, rezoning or other changes to currently vacant land that could greatly increase value | Only small number of private parcels need to be purchased, risk is covered in base cost variation. | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.03 | Additional right of way required | Additional right of way required | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.05 | FHWA may not allow RFP to be released prior to Right of Way certification | This risk will be mitigated by getting DB ROW certification with conditions. | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.06 | Right of way acquisition is more costly than expected due to landowner objections | Already covered in the base cost variation | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.07 | Less right of way may be needed (opportunity) | Already covered in the base cost variation | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.08 | Additional right of way required for pedestrian accommodations | Additional right of way required for pedestrian accommodations | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.09 | Right of way easements for drainage | Right of way easements for drainage | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.10 | Right of way unable to certify the project before advertising | Right of way unable to certify the project before advertising | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.11 | Additional right of way required | RFP will have restriction on Right of Way. If additional ROW is required the DB contractor will be responsible for it. Potentially acquiring ROW on the Southside of MDX but will cause a reevaluation of PD&E that would delay the project schedule. | Right of Way
Initial |  | I-395 Reconstruction |  | FL | ROW.12 | Crossing several rail roads, Metro Rail, aerial rights and TCEs | Base cost estimate is for flagger for FEC and spotters for the Metro Rail. No major concerns foreseen. Have not had problems with FEC on previous projects. | Traffic
Initial |  | I-395 Reconstruction |  | FL | CNS.01 | Railroad involvement | Railroad involvement | Right of Way
Initial |  | I-395 Reconstruction |  | FL | CNS.06 | Work windows | Working on the existing pier of metro mover is restricted to occur between 1 am to 5 am. The base schedule already account for that. | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.08 | Encountering unexpected subsurface conditions | Have done extensive geotechnical surveys in the area, and are comfortable with the subsurface conditions. Test piles could indicate longer pile length but the geotechnical profile has been consistent. | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.09 | Different site conditions | This risk cover different sites on this project one example is on MDX where current design assumes using micro pile near the historical homes where there are existing battered piles so there maybe challenges. Use of micro pile has been approved from the state geotechnical office. Could require in the RFP that the contractor can not add a new column to minimize impact to the historical properties. | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.09 | Different site conditions | This is a global risk that covers different site condition. One example is the Arsht Center garage, former Greyhound parcel | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.09 | Different site conditions | This is a global risk that covers different site condition. Cost impact is based on higher cost on previous project | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.10 | Coordination with local agencies | Potential issue on the maintenance on the pump station but will not impact the project. | Stakeholder
Initial |  | I-395 Reconstruction |  | FL | CNS.11 | Interference from other projects | Interference from other projects | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.11 | Interference from other projects | There is also adjacent project that could potentially require coordination but should not affect the project schedule or cost | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.13 | Alternate route issues | Not a concern on this project. There is alternate route that can be used. Most closure would be night time closure | Traffic
Initial |  | I-395 Reconstruction |  | FL | CNS.15 | Other construction projects in region limit supply / cost of materials | Discussed in market conditions risks. | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.16 | Other construction projects in region limit supply / cost of labor | Discussed in market conditions risks. | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.17 | Pressure to deliver project on an accelerated schedule | This is DB it will allow for acceleration. No mandate to finish the project on a specific date. There will be financial incentive to deliver the project early but it will not be counted as a project cost. This is captured in DES.19. | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.19 | Conflict between adjacent projects | Conflict between adjacent projects | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.20 | Material Availability - Cost of embankment | Material Availability - Cost of embankment | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.21 | Weather related interruptions to construction | Due to weather could anticipate a 5 to 6 months delay but they are non compensable days. (30 days per year) | Construction
Initial |  | I-395 Reconstruction |  | FL | CNS.22 | Work hour restrictions for some activities due to noise | Work hour restrictions for some activities due to noise | Environmental
Initial |  | I-395 Reconstruction |  | FL | CNS.24 | Impact due to special events | Potential impact due to special events. Need to identify events where lane closure is not allowed in the RFP. The known events will be accounted for in the RFP however if new events arise it could affect the project schedule. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.02 | Unsuitable / contaminated materials | Related to dolphin and pile removal, there is naturally occurring arsenic on the bay bottom. There could be additional cost for disposal of material. This applies to the removal of 4 existing dolphins and during the removal of existing piles. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.05 | Concrete delivery | The plan would be to bring concrete on trucks via barges to the bridge. During the first stage it could be beneficial to bring the concrete batch on the west side and move it to the east side when the northbound bridge is being constructed this is because the barges can only pass through the shipping channels and that could delay concrete delivery. Contractor may or may not use batch plant for concrete. May use off site concrete plant or on site or barge batch plant. Risk accounts for cost premium to deliver concrete to site. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.08 | Different site conditions | This risk item captures any conflicts between new piers and existing man made object on the bottom of the bay or underground. (Already accounted for different geotechnical conditions in Geotech risk items and contractor is responsible for conducting his own investigation. The cost for the investigation is accounted for in the base cost.) | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.11 | Weather related interruptions to construction | Contractor will have large equipment on the water which could be potentially impacted for almost half a year over the total duration of construction by severe weather. The time to move off site could impact project schedule. For storm events as well as regular weather days. Bad weather condition include severe storm events, cold weather, and bad condition on the bay. The weather impact could also affect where materials are being produced not just the project location. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.02 | Changing assumptions on technical design issues in pre-design stage | Changing assumptions on technical design issues in pre-design stage | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.10 | Delay in design reviews (internal or external) for post-design NTP | Potential for delays with reviews from local agencies and coordination with FHWA. Typically 2 review periods of 3 weeks. Could have to potential delay for comments from local agencies. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.08 | legal sufficiency | Issue that came up from the Public Hearing has been addressed. Small chance of delay if FHWA legal depart has backlog. Risk has been retired as the activity impacted (PD&E) is not complete without any schedule delays. | Procurement and contracting
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.10 | Expected controversy on environmental grounds | Many issues have already been addressed. Haven't received any letters from Env groups. At this point, project will have a level 2 type of aesthetics but need to be more detailed about what will be included in the Aesthetics. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.13 | Environmental Permits or agency actions delayed or take longer than expected | Need permits from DEP, coast guard, USACE, been coordinating with these agencies. The plan is for design builder to obtain the permits. The permitting agencies are onboard with this project, project considered a priority for them. Current Base schedule is 6 months after design NTP. Potential for delay in obtaining these permits from 1 to 6 months depending on the contractor design. To mitigate this risk will inform the contractor about the permits needed for this project. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.13 | Potential for land donation from the city | Potential for land donation from the cities. Base cost account for 5percent variability dues to changes in design | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.01 | Design changes on bridge substructure | Potential savings for precasting the piers, changing the pile type, changing pile design. The base substructure cost is $240 million, the most likely quantification is about 10% of the base substructure cost. Schedule savings based on reduction observed on other projects relative to the base schedule estimates. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.02 | Design changes on bridge superstructure | Potential savings from changes in the span link at the channel. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.09 | Pedestrian overlook add-on to bridge | Not part of the concept plan. There is no commitment in doing it. | Traffic
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.10 | Change in bridge aesthetic design | Color concrete will be used in this project. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.13 | Aesthetic modifications to lighting on the bridge | Accounted for in the base cost. Based cost is based on a similar type of project. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.14 | Scour considerations | The majority of the impact already accounted for in the sub-structure modification. | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.18 | Intersection modification at 17th Ave. | The locals prefer a no signal option. One option could be for the fly-over. A fly-over is not part of the preferred alternative, will need major revaluation. The RFP maybe structured in a manner to encourage contractor innovation at this location. The issue is the large schedule impact due to the PD&E process. If it is included it will need to be part of the contract duration. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.19 | Changing geotechnical conditions in bridge approaches | This risk item addresses Geotech conditions within the bridge approach area, such as soil stability in the fill areas. No current issue on the existing bridge, should expect the same conditions. | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.04 | Utility relocation costs may be responsibility of project | Current base utility cost is 0, and haven't received any reimbursement letter. If DB contractor has different design that affect utility it will be the contractor responsibility | Utilities
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.01 | Erosion control | The current design doesn't include ponds. Will require temp ponds. Potential for treating the water. The base cost need to be adjusted | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | TMT.02 | Incident management | Contractor will be responsible for responding to incidents during construction. Could be included in the contract for the contractor to provide some incident management plan. Cost impact for potential extra costs beyond the base for incident management, for example having a dedicated tow truck during construction. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | TMT.06 | Maintaining CCTV camera line of sight to all areas of the bridge. | Planning to upgrade system prior to first traffic shift. Not an issue as long as it doesn't conflict with the contractor operation. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.03 | Staging area for barges and materials | Concerns about some of the areas identified, could have problem with access and staging for material. The cost for staging areas is typically accounted for in mobilization using 10% should be sufficient. Currently not quantified - monitor going forward. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.04 | Pile installation | Currently proposed design uses a proprietary pile system for which there is only one supplier in the region, however the contractor will not be restricted on choosing a particular pile. Regardless of the pile type, there may be potential issues with pile driving vibration and actual or perceived impact to propriety owners. The range on bridge structure base cost unit price should account for this risk. Need to track this in the base cost going forward. | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.06 | Opportunity to overlap Phase 1 and 2 | Revised base schedule to show that construction will start 6 months after NTP. This opportunity no longer exists | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.07 | Change in design during construction | Have accounted for this in structures and design risk items. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.09 | Encountering unexpected subsurface conditions | Have accounted for in Geotech risk items and in CNS08 | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.10 | Impacts on final paving due to weather | Not a problem as long as it doesn't fall in the winter months. Not an issue at this point. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.12 | Work windows / time of day restrictions | Already captured in other risk items | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.13 | Height restriction and airport proximity | Early coordination with FAA, requires form 7460 for temporary airspace obstructions for tall construction equipment use (cranes, etc.). Risk accounts for potential schedule delays in getting the 7460 approved. Could add in the RFP that DB builder is required to get the approval prior to the start of construction | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.14 | Impact of special events on construction duration | Will provide the same number of lanes as there are today during construction. Contractor will be made aware of special events in the RFP. Not an issue. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.15 | Impacts to marine traffic during construction | Should address any issue (coordinate and comply) with Coast guard, should be able to resolve any issue. As long as the expectation of the coast guard are clearly defined don't foresee any problems. Could potentially include that in the RFP as far as time frame restriction. | Traffic
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.16 | Safety issues delay project opening | Safety issues delay project opening | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.17 | Coordination with adjacent projects during construction | Minor local gov't risk, commercial development on Gulf Breeze side. Not an issue. RFP includes requirement to coordinate with local projects | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.18 | Demolition production rate | Assume aggressive demolition production rate of 2000 SF/day. The recommended statewide production rate is between 270-600 SF/day. This should not be an issue project team is comfortable with the base duration and the contractor would be required to bid time. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.19 | Noise impact during construction | During construction, potential concern with pile driving. Base schedule does not currently assume night pile driving therefore won't impact current project cost or schedule. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | CNS.20 | Availability of borrow material | Project is borrow job, should have sufficient supply locally and parks will be used for material staging. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.01 | Change in alternative | DB firm could propose a different alternative. Small probability that it could happen with a big impact on schedule. DB will be responsible of re-evaluation process. 4f will have a big impact on schedule that's why don't foresee that DB will come up with a new alternative. Base cost and schedule assumes central west alternative. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.03 | Changes to construction packaging and phasing | Changes to construction packaging and phasing | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.04 | Design variations not approved | There are no anticipated design exceptions for this project, but there are 3 design variations proposed at this time: 1) Design variation for cross slope at Bay front Parkway at pavement tie-in point; 2)Border width (should not be an issue to get approved); anticipate both to be approved. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.05 | Changes in alignment based on 4f document, affecting design cost and construction cost. Will be covered in ENV risk item | What's in the base is the lowest 4f impact in the central west option which is the base. Additional 4f mitigation addressed in ENV risk items. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.06 | Changes in pavement section design, pavement spec changes, legal load issue, and effect on life cycle decisions on pavement design | No PTSR. RFP will provide minimum pavement design requirement. Not a major risk. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.07 | Uncertain quantity of noise walls required | There are likely no areas that meet the criteria for sound walls. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.08 | Potential changes to design of permanent traffic items (ITS, Illumination, Intersection, etc.) | Base cost should be sufficient for ITS element, Under-bridge lighting is an aesthetic item in the bridge cost estimate. Base cost assumes standard roadway lighting (i.e.: not decorative). | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | DES.09 | Delay in design reviews (internal or external) for pre-design NTP | Potential for delays with reviews from local agencies and coordination with FHWA. Very minimal schedule impacts. Have already addressed most 4f issues, currently awaiting final approval from FHWA don't anticipate any delay. Not a concern for delay leading up to Pre-Design NTP | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.01 | Drainage design enhancement | Advanced drainage design in the last year, and Haven't encountered any problem so far with drainage at the green shore. | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.03 | Additional Right of Way related to drainage required | With compensatory drainage requirement there could be additional ROW acquisition, but likely not an issue | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.04 | Construction quality / quantity issues | DEP will require permitting regarding nutrient removal calculations for the bridge and water treatment system . This is a new requirement that should not have an impact on the project cost and schedule. Street sweeping program will still be continued. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.05 | Determination of wetlands impacts | Small impact to salt water marsh, on both sides. Not a risk accounted for in the base, but impacts would be small or negligible. The base account for $28K in Env mitigation. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.06 | Hazardous materials found during construction | Contamination and screening evaluation, found a minor contamination site (dive center formally a gas station) affecting a small area. Should not be a significant cost impact ($25 to 50k impact) - base cost adequately addresses this issue. Contamination is programmed outside the project. Potential contamination is on the roadway approach which doesn't drive the production schedule but could result in some MOT shift. Contamination should not have an impact on the project schedule. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.07 | Delay in environmental evaluation due to 4f impact | Critical element is the 4f acceptance by FHWA. Base schedule requires FONSI by 12/2013, which implies the Section 4(f) impacts have also been approved by FHWA. Concern is potential for delay in review time and request for additional information, rather than rejection of plan. Need agreement from both cities following the public hearing. Received letter of approval from one city, concurring that they have provided the necessary mitigation. Don't foresee any delay. Still waiting from a letter of approval from the Gulf breeze, but don't foresee any problem. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.09 | Unexpected environmental involvement | Not an issue. Had a lot of public involvement. Major issue is 4f which is addressed in other risks. Project plans to avoid cultural and historical areas. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.11 | Section 4(f) Environmental mitigation enhancements | This is now retired the base cost include the 4f mitigation | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.12 | New Environmental permits or new information required | May need to coordinate on Green Shore impact as part of DEP permit. The current design avoid impact to it. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ENV.14 | Impact to salt water marsh | The cost is captured in environmental mitigation base cost. Impacts are estimated at 0.07 acres. | Environmental
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.02 | Delay in Right of Way acquisition | Within the RFP DOT will specify the ROW limits, the design builder can't go outside these limits. | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.03 | right of way acquisition delays construction | right of way acquisition delays construction | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.04 | Delay in right of way document internal approval process | Delay in right of way document internal approval process | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.05 | Right of Way requirements delivered late or are inadequate | Right of Way requirements delivered late or are inadequate | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.07 | Additional right of way acquisition costs to resolve upside down mortgage issues | Additional right of way acquisition costs to resolve upside down mortgage issues | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.08 | Higher real estate cost due to development, annexation, rezoning or other changes to currently vacant land that could greatly increase value | Higher real estate cost due to development, annexation, rezoning or other changes to currently vacant land that could greatly increase value | Traffic
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.09 | Additional right of way required | Additional right of way required | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.10 | Potential to not acquire right of way for flyover now if it is not constructed | Potential to not acquire right of way for flyover now if it is not constructed | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | ROW.12 | Additional right of way for drainage | Additional right of way for drainage | Right of Way
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.05 | Addition of bridge crossover for incident management | Risk Retired. Can use the shoulder(12ft) that can be used for incident management | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.06 | Foundation abutment and approach wall | Base assume cast in place for abutment and retaining walls. MSE wall can not be applied in this area due to storm surge environment | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.11 | Changes in structure and embankment | Profile is well defined no reason to lower it or raise it. Team confident on the storm surge analysis, which dictates the roadway profile. | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.20 | Changes in pile length | Captured in change in foundation risk item | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.21 | Change in foundations | Mitigated the risk by conducting additional borings. Result of the additional borings is in line with what is expected. Potential changes in foundation are captured in STG 01 | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.22 | Subgrade issues | Do not have land base boring but profiles are being raised above current condition. Not an issue | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | STG.24 | Geotechnical surveys late | Already conducted Geotech investigation. Could conduct additional investigation to provide additional information during RFP, but surprises are not expected. | Structure and Geotechnical
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | TMT.01 | Traffic management | Traffic management | Traffic
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | TMT.04 | Extraordinarily complex staging / maintenance of traffic | Extraordinarily complex staging / maintenance of traffic | Traffic
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | TMT.05 | Maintaining local access | Challenge could be during the arterial median/island construction of the project, however contractor should be able to work around this and maintain local access. | Traffic
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | TMT.07 | Contractor access points | Contractor access points | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.01 | AT&T temporary and ultimate relocation | May need to relocate AT&T on the Pensacola side during construction. This is already accounted for in the base schedule. | Utilities
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.02 | Utility relocation may not happen on time | Phase 1 has 200 days for utility relocation. Under DB contract utility coordination will be the contractor responsibility. Contractor will probably coordinate with utilities to minimize schedule impact. Should have sufficient time in the base schedule. | Utilities
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.03 | Design changes | Design changes | Design
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.05 | Impact to gas line | Located east of the bridge follow east side of the edge of pavement in Pensacola, then just outside the row on the other side of the road and crosses the other side of the road. Gas line likely need to be relocated in the parking area on the Gulf Breeze side. | Utilities
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.06 | Impact to fiber optic line | Impact to fiber optic line | Utilities
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.07 | Impact to water line | Impact to water line | Utilities
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.08 | work windows | No known work window restriction and given the time frame should be able to work around it. | Construction
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.09 | Finding existing utilities during construction | PD&E should capture all major utilities. Not an issue | Utilities
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.10 | Delay in agreements | Delay in agreements | Stakeholder
Initial |  | Three Mile Pensacola Bay Bridge |  | FL | UTL.11 | Impact on railroad | RR in proximity on Pensacola already an elevated crossing today. There has been coordination with RR and there is no impact. | Right of Way
Initial |  | I-94 North-South |  | WI | De1 | Changes in Design | Change in barrier standards have increase base estimate by approximately $11M. Overall risk is LOW. | Design
Initial |  | I-94 North-South |  | WI | De3 | Redesign at Route 50 | Redesign at Route 50 | Design
Initial |  | I-94 North-South |  | WI | De4 | Construction Contract Packaging | Breaking up large package into smaller packages for contract | Procurement and contracting
Initial |  | I-94 North-South |  | WI | De5 | Design Changes | Design changes due to projects being at different levels of design | Design
Initial |  | I-94 North-South |  | WI | TM1.a | Traffic Management - baseline solution does not work (late) | Traffic control will involve maintaining two lanes of traffic at all times during construction along I94 mainline. This includes adding temporary widening in stage 1. The risk is that the temporary widening to maintain 2 lanes of traffic in each direction may not work, and may need to maintain 3 lanes of traffic in each direction. Overall risk is LOW. | Traffic
Initial |  | I-94 North-South |  | WI | TM1.b | Traffic Management - baseline solution does not work (late) | Traffic control will involve maintaining two lanes of traffic at all times during construction along I94 mainline. This includes adding temporary widening in stage 1. The risk is that the temporary widening may fail during construction. Overall risk is LOW. | Traffic
Initial |  | I-94 North-South |  | WI | TM2 | Traffic Management - baseline solution does not work (early) | Traffic control will involve maintaining two lanes of traffic at all times during construction along I94 mainline. This includes adding temporary widening in stage 1. The risk is that the temporary widening to maintain 2 lanes of traffic in each direction may not work, and may need to maintain 3 lanes of traffic in each direction. Overall risk is LOW. | Traffic
Initial |  | I-94 North-South |  | WI | TM2.a | Traffic Management - baseline solution does not work (late) | Traffic control will involve maintaining two lanes of traffic at all times during construction along I94 mainline. This includes adding temporary widening in stage 1. The risk is that the temporary widening to maintain 2 lanes of traffic in each direction may not work, and may need to maintain 3 lanes of traffic in each direction. Overall risk is LOW. | Traffic
Initial |  | I-94 North-South |  | WI | TM3 | Traffic Management - baseline budget not significant | Traffic control will involve maintaining two lanes of traffic at all times during construction along I94 mainline. This includes adding temporary widening in stage 1. The risk is that the temporary widening to maintain 2 lanes of traffic in each direction may not work, and may need to maintain 3 lanes of traffic in each direction. Overall risk is LOW. | Traffic
Initial |  | I-94 North-South |  | WI | TM10 | ATT&T Fiber Optic Line for ITS usage | ATT&T Fiber Optic Line for ITS usage | Utilities
Initial |  | I-94 North-South |  | WI | SG8 | Cost savings opportunity from modifying tunnel design | Cost savings opportunity from modifying tunnel design | Design
Initial |  | I-94 North-South |  | WI | SG10 | Changing the tunnel design | Changing the tunnel design | Design
Initial |  | I-94 North-South |  | WI | SG10b | Abandonment of alternate tunnel design during construction | Abandonment of alternate tunnel design during construction | Design
Initial |  | I-94 North-South |  | WI | SG11 | Tunnel cover earthwork and paving weather issues | Winter could come early require changes to the tunnel cover earthwork and paving due to cold weather. | Construction
Initial |  | I-94 North-South |  | WI | SG13 | Changes in pile length due to dynamic pile monitoring | Changes in pile length due to dynamic pile monitoring | Structure and Geotechnical
Initial |  | I-94 North-South |  | WI | Co1 | Encountering unexpected subsurface conditions | There is significant grading, profile changes, and structures along this corridor. As a result the design team has done an aggressive program of geotechnical investigation. This has reduced the risk of encountering unexpected subsurface conditions. Current pavement designed has also reduced the risk with the breaker run and 3-inch asphalt subbase layer. However, due to the massive scale of this project geotechnical issues still pose a risk. Overall risk is LOW to MEDIUM. | Construction
Initial |  | I-94 North-South |  | WI | Co3 | Materials Delivery Constraints (On-site) | For Kenosha/Racine Counties, northbound lanes will be constructed with traffic on southbound lanes and vise versa. Material will be hauled on State/County highways. Some local roads may be affected. There is also the frontage road system that the contractor can utilize. In Milwaukee there will be well defined access points for delivery of material. Steel and concrete will be brought in non-locally. The increased costs have been reflected in the estimate to some extent. Overall risk is MEDIUM TO HIGH. | Construction
Initial |  | I-94 North-South |  | WI | Co13 | Additional Temporary Sound walls required for construction noise abatement | Sound walls were covered in the Base estimate. New sound walls potentially located at Oakwood. | Environmental
Initial |  | I-94 North-South |  | WI | Co18 | Weather related interruptions to construction (Mitchell Interchange, incl. Tunnels) | Winter season and a wet spring/summer will cause delays. There is significant grading and exposed grade that will be subject to the weather. The proposed pavement structure includes a 3 inch asphalt subbase that will reduce the exposure of the subbase. Overall risk is MEDIUM to HIGH. | Construction
Initial |  | I-94 North-South |  | WI | Co18.b | Weather related interruptions to construction (others) | Winter season and a wet spring/summer will cause delays. There is significant grading and exposed grade that will be subject to the weather. The proposed pavement structure includes a 3 inch asphalt subbase that will reduce the exposure of the subbase. Overall risk is MEDIUM to HIGH. | Construction
Initial |  | I-94 North-South |  | WI | ED5 | Unanticipated Hazardous Materials or Contaminated Soils | Unanticipated Hazardous Materials or Contaminated Soils | Environmental
Initial |  | I-94 North-South |  | WI | ED6 | Unanticipated Cultural or Archaeological Findings | Unanticipated Cultural or Archaeological Findings | Environmental
Initial |  | I-94 North-South |  | WI | ED24 | Major Storm | Erosion Control issues with major storm | Construction
Initial |  | I-94 North-South |  | WI | ED26 | Individual Envrionmental Permit from Corps of Engineers (COE) for CTH C Interchange | Individual Envrionmental Permit from Corps of Engineers (COE) for CTH C Interchange | Environmental
Initial |  | I-94 North-South |  | WI | Rw1 | Objections to Right of Way appraisal takes more time and/or money (litigation cost) | There will be objections, will not hold up construction but will require mitigation. Additional $15M has been allocated to litigation. Overall risk is LOW to MEDIUM. Condemnations and Litigation. | Right of Way
Initial |  | I-94 North-South |  | WI | Rw1a | Additional Condemntation of Properties near STH 20 due to Stimulus | Additional Condemntation of Properties near STH 20 due to Stimulus | Right of Way
Initial |  | I-94 North-South |  | WI | Rw2 | Right of Way Acquisition is more costly than expected (market driven) | Right of Way Acquisition is more costly than expected (market driven) | Right of Way
Initial |  | I-94 North-South |  | WI | Rw3 | Additional Right of Way may need to be acquired (refinement of design) | Plats for Kenosha and Racine interchanges have been completed. Other areas the plats are near completion. In Milwaukee County the south segment the plats are preliminary. The plats in the Mitchell Interchange is completed. Overall risk is LOW. | Right of Way
Initial |  | I-94 North-South |  | WI | Ut5 | Discovery of unknown utilities during construction | Finding unknown utility during construction, most likely municipal. | Utilities
Initial |  | I-94 North-South |  | WI | De2 | Need for design exceptions | Need for design exceptions | Design
Initial |  | I-94 North-South |  | WI | De7 | Design changes when working "at risk" | Design changes when working "at risk" | Design
Initial |  | I-94 North-South |  | WI | De8 | Flaw in design is discovered, requires more time to alter design than is originally planned. | Flaw in design is discovered, requires more time to alter design than is originally planned. | Design
Initial |  | I-94 North-South |  | WI | De9 | Design incomplete or in error (during design) | Design incomplete or in error (during design) | Design
Initial |  | I-94 North-South |  | WI | De10 | Inaccurate assumptions on technical issues in design stage (need updating) | Inaccurate assumptions on technical issues in design stage (need updating) | Design
Initial |  | I-94 North-South |  | WI | De12 | Hazardous waste site analysis incomplete or in error | Hazardous waste site analysis incomplete or in error | Environmental
Initial |  | I-94 North-South |  | WI | De13 | Change requests because of errors | Change requests because of errors | Procurement and contracting
Initial |  | I-94 North-South |  | WI | De17 | Schedule constraints | Schedule constraints | Construction
Initial |  | I-94 North-South |  | WI | De18 | 8-lane compatibility design | 8-lane compatibility design | Design
Initial |  | I-94 North-South |  | WI | De19 | Noise mitigation | Noise mitigation | Environmental
Initial |  | I-94 North-South |  | WI | De20 | Design review delays project schedule | Design review delays project schedule | Design
Initial |  | I-94 North-South |  | WI | De21 | Design changes impact construction costs and schedule | Design changes impact construction costs and schedule | Design
Initial |  | I-94 North-South |  | WI | PM1 | Pressure to deliver project on an accelerated schedule (design) | Pressure to deliver project on an accelerated schedule (design) | Construction
Initial |  | I-94 North-South |  | WI | PM2 | Local agency issues | Local agency issues | Stakeholder
Initial |  | I-94 North-South |  | WI | PM3 | Contractor delays and low performance | Contractor delays and low performance | Construction
Initial |  | I-94 North-South |  | WI | PM4 | Project scope definition is poor or incomplete | Project scope definition is poor or incomplete | Management and Funding
Initial |  | I-94 North-South |  | WI | PM5 | Change in key staffing during the project | Change in key staffing during the project | Organizational
Initial |  | I-94 North-South |  | WI | PM6 | Inexperienced workforce / inadequate staff | Inexperienced workforce / inadequate staff | Organizational
Initial |  | I-94 North-South |  | WI | PM7 | Public awareness / support | Public awareness / support | Stakeholder
Initial |  | I-94 North-South |  | WI | PM8 | No control over / issues with staff priorities | No control over / issues with staff priorities | Organizational
Initial |  | I-94 North-South |  | WI | PM11 | Communication breakdown with project team | Communication breakdown with project team | Stakeholder
Initial |  | I-94 North-South |  | WI | PM12 | Lack of coordination | Management is by county, there is a corridor management team (CMT) that oversees the counties. | Stakeholder
Initial |  | I-94 North-South |  | WI | PM13 | Lack of upper management support | Lack of upper management support | Organizational
Initial |  | I-94 North-South |  | WI | PM14 | Priorities change on existing program | Priorities change on existing program | Organizational
Initial |  | I-94 North-South |  | WI | PM15 | Loss of critical staff during project | Loss of critical staff during project | Organizational
Initial |  | I-94 North-South |  | WI | PM17 | Delay getting management approvals, decisions | Delay getting management approvals, decisions | Management and Funding
Initial |  | I-94 North-South |  | WI | PM18 | Functional units not available, overloaded | Functional units not available, overloaded | Organizational
Initial |  | I-94 North-South |  | WI | PM20 | Construction Management Strains from Accelerated Schedule | Construction Management Strains from Accelerated Schedule | Construction
Initial |  | I-94 North-South |  | WI | TM4 | Traffic Management - staging | Any delay in adjacent projects may impact staging for future work. This risk affects early work in Kenosha and the Mitchell Interchange. Overall risk is LOW. | Traffic
Initial |  | I-94 North-South |  | WI | TM6 | Delay in delivery of Traffic and ATMS items | Delay in delivery of Traffic and ATMS items | Traffic
Initial |  | I-94 North-South |  | WI | TM7 | Length of Work Zones | Length of Work Zones | Construction
Initial |  | I-94 North-South |  | WI | TM8 | Maintaining contractor access | Maintaining contractor access | Construction
Initial |  | I-94 North-South |  | WI | TM9 | Incident management | Base estimate includes traffic mitigation money with up to $20M set aside for patrol contracts - state and service patrols, as well as PI outreach. | Construction
Initial |  | I-94 North-South |  | WI | TM12 | Winter operations | Schedule accounts for winter shutdowns; baseline plan is that traffic will be back on mainline alignment by winter shutdown (normal operations). Risk of early snow. Covered in weather related risk (Ex4). | Construction
Initial |  | I-94 North-South |  | WI | TM14 | Access points | Access points | Construction
Initial |  | I-94 North-South |  | WI | SG1 | Unexpected geotechnical issues - Additional Base Required | Pavement design has included geotechnical concerns. | Structure and Geotechnical
Initial |  | I-94 North-South |  | WI | SG3 | Geotechnical surveys late and/or surveys in error | Geotechnical surveys late and/or surveys in error | Structure and Geotechnical
Initial |  | I-94 North-South |  | WI | SG4 | Geotechnical / foundation in error | Geotechnical / foundation in error | Structure and Geotechnical
Initial |  | I-94 North-South |  | WI | SG7 | Cost Savings Opportunity for Redecking bridges | Cost Savings Opportunity for Redecking bridges | Design
Initial |  | I-94 North-South |  | WI | Co2 | Material availability | Base material aggregates supply should be good. With HPC pavement, there are no local pits to supply the aggregate. Steel material unit prices have been adjusted to reflect past shortages. Over risk is MEDIUM to HIGH. | Construction
Initial |  | I-94 North-South |  | WI | Co4 | Different site conditions | The aggressive geotechnical investigation has reduced this risk. | Construction
Initial |  | I-94 North-South |  | WI | Co5 | Inaccurate contract time estimates | The yearly base schedule is establish from individual project production rates. The overall program schedule is established from the funding process. As projects are combined the production rates are adjusted. Rural interstate area should not be an issue | Construction
Initial |  | I-94 North-South |  | WI | Co6 | Buried man-made objects | As part of the Environmental investigation for the corridor and the separate interchanges hazardous waste locations have been identified. This has been done on a project level and a corridor level. These sites will be mitigated prior to construction and s | Construction
Initial |  | I-94 North-South |  | WI | Co8 | Multiple Primes Performance | Smaller contracts will be Let to provide potential DBE opportunities. These contracts will be non-critical and coordinated with the larger contracts. Overall risk is LOW. | Construction
Initial |  | I-94 North-South |  | WI | Co9 | Interference from other projects | Interference from other projects | Construction
Initial |  | I-94 North-South |  | WI | Co10 | Nonconforming work results in schedule delay and additional costs | The construction work involves grading, pavement, structures, and other traditional work. The one unique item is the tunnels in the Mitchell Interchange. This construction is on an aggressive schedule. Overall risk for tunnels is MEDIUM | Construction
Initial |  | I-94 North-South |  | WI | Co12 | Length of day/season restrictions | The project will follow all local ordinances within city limits. It is anticipated that night work is needed to meet the aggressive timelines. The base estimate accounts for additional night work. If any work is accelerated then night work or winter work | Construction
Initial |  | I-94 North-South |  | WI | Co14 | Safety issues delay project opening | There is an Owner Controlled Insurance Program (OCIP) to be used on this project. It will be implemented throughout the duration of construction and will reduce contractor's accident. Overall risk is LOW to N/A | Construction
Initial |  | I-94 North-South |  | WI | Co15 | Permit work windows | Permit work windows | Construction
Initial |  | I-94 North-South |  | WI | Co16 | Labor union strike or other labor issues interrupt construction. | Labor union strike or other labor issues interrupt construction. | Management and Funding
Initial |  | I-94 North-South |  | WI | Co17 | Environmental Permitting | Environmental Permitting | Environmental
Initial |  | I-94 North-South |  | WI | ED2 | Section 106 issues of National Environmental Policy Act Review (NEPA) | Section 106 issues of National Environmental Policy Act Review (NEPA) | Environmental
Initial |  | I-94 North-South |  | WI | ED3 | Section 4(f) resources affected National Environmental Policy Act Review (NEPA) | Section 4(f) resources affected National Environmental Policy Act Review (NEPA) | Environmental
Initial |  | I-94 North-South |  | WI | ED4 | Additional Urban Drainage Design Cost | Mitchell Interchange area requires additional storage. Coordinating with MMSD. Overall risk is LOW. | Design
Initial |  | I-94 North-South |  | WI | ED7 | Negative community impacts expected | Coordinating with the locals for potential impacts | Stakeholder
Initial |  | I-94 North-South |  | WI | ED8 | Hazardous waste preliminary site investigation required | Hazardous waste preliminary site investigation required | Environmental
Initial |  | I-94 North-South |  | WI | ED9 | Historic site, endangered species, wetlands present | Historic site, endangered species, wetlands present | Environmental
Initial |  | I-94 North-South |  | WI | ED10 | Environmental Permits or agency actions delayed or take longer than expected | Environmental Permits or agency actions delayed or take longer than expected | Environmental
Initial |  | I-94 North-South |  | WI | ED12 | Environmental New permits or new information required | Environmental New permits or new information required | Environmental
Initial |  | I-94 North-South |  | WI | ED13 | Environmental regulations change | Environmental regulations change | Environmental
Initial |  | I-94 North-South |  | WI | ED14 | Environmental analysis on new alignments is required | Environmental analysis on new alignments is required | Environmental
Initial |  | I-94 North-South |  | WI | ED15 | Formal National Environmental Policy Act Review (NEPA) consultation is required | Formal National Environmental Policy Act Review (NEPA) consultation is required | Environmental
Initial |  | I-94 North-South |  | WI | ED17 | Project in an area of high sensitivity for paleontology | Project in an area of high sensitivity for paleontology | Environmental
Initial |  | I-94 North-South |  | WI | ED19 | Water quality issues | Water quality issues | Environmental
Initial |  | I-94 North-South |  | WI | ED20 | Growth inducement / sprawl issues | Growth inducement / sprawl issues | Traffic
Initial |  | I-94 North-South |  | WI | ED22 | Reviewing agency requires higher-level review than assumed | Reviewing agency requires higher-level review than assumed | Management and Funding
Initial |  | I-94 North-South |  | WI | Rw4 | Staffing - Consultant Appraisers | Staffing - Consultant Appraisers | Organizational
Initial |  | I-94 North-South |  | WI | Rw6 | Risk of acquiring additional access | Risk of acquiring additional access | Construction
Initial |  | I-94 North-South |  | WI | Rw7 | right of way unable to certify the project before advertising | right of way unable to certify the project before advertising | Right of Way
Initial |  | I-94 North-South |  | WI | Rw8 | Delays in right of way acquisition due to landowner objections to project. | Delays in right of way acquisition due to landowner objections to project. | Right of Way
Initial |  | I-94 North-South |  | WI | Rw9 | Refusal of land owners to sell requires route change, necessitates a change in design. | Refusal of land owners to sell requires route change, necessitates a change in design. | Right of Way
Initial |  | I-94 North-South |  | WI | Rw10 | Less right of way than anticipated may be needed (opportunity) | Less right of way than anticipated may be needed (opportunity) | Right of Way
Initial |  | I-94 North-South |  | WI | Rw12 | Schedule constraints | Schedule constraints | Construction
Initial |  | I-94 North-South |  | WI | Rw13 | Additional wetlands mitigation area needed | Additional wetlands mitigation area needed | Environmental
Initial |  | I-94 North-South |  | WI | Ut1 | Failure to obtain necessary utility agreements or acquisitions prior to construction | Potential for conflicts between utilities and contractor under accelerated projects. Under the base schedule this should not be a risk. Overall risk is LOW. | Utilities
Initial |  | I-94 North-South |  | WI | Ut2 | Major Utility Installations conflicts | There is a potential conflict with the AT&T fiber optic being relocated prior to or during construction in Kenosha and Racine Counties. Overall risk is LOW. | Utilities
Initial |  | I-94 North-South |  | WI | Ut3 | Design changes | Design changes | Design
Initial |  | I-94 North-South |  | WI | Ut4 | Utility relocation may not happen in time | Utility relocation may not happen in time | Utilities
Initial |  | I-94 North-South |  | WI | Ut6 | Available room for utility relocations | Available room for utility relocations | Utilities
Initial |  | I-94 North-South |  | WI | Rr1 | Impact on Railroad Operations | Impact on Railroad Operations | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW -50-1 | Condemnation and administrative settlements added Right of Way costs | Condemnation and administrative settlements added Right of Way costs | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW -50-1 | Condemnation and administrative settlements added Right of Way costs | Condemnation and administrative settlements added Right of Way costs | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-900-1 | Optimization of Right of Way | The opportunity is that less right-of-way would be needed. Potential opportunity for developer to not need as much as estimated and/or ATC development may reflect less right-of-way is needed. The assumed base is around $700M | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-900-1 | Optimization of Right of Way | The opportunity is that less right-of-way would be needed. Potential opportunity for developer to not need as much as estimated and/or ATC development may reflect less right-of-way is needed. The assumed base is around $700M | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-60-3 | Required Additional Right of Way | changes could lead to more or less right-of-way required. Design is currently less than 30% (approx. 15%) . More or less right-of-way could be needed due to drainage, construction easements, utility easements, slope easements, etc. | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-60-3 | Required Additional Right of Way | changes could lead to more or less right-of-way required. Design is currently less than 30% (approx. 15%) . More or less right-of-way could be needed due to drainage, construction easements, utility easements, slope easements, etc. | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-60-4 | Added right of way | Additional Right of way is required | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-60-4 | Added right of way | Additional Right of way is required | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-60-10 | Relocation Requirements for Right of Way | Delays due to right-of-way acquisition affect project schedule. If ADOT maintains that they will acquire all the parcels, they will retain the risk of delay to the developer. Every day will incur an extended overhead cost. The base schedule assumes right-of-way being complete 12 months prior to the completion of construction. | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-60-10 | Relocation Requirements for Right of Way | Delays due to right-of-way acquisition affect project schedule. If ADOT maintains that they will acquire all the parcels, they will retain the risk of delay to the developer. Every day will incur an extended overhead cost. The base schedule assumes right-of-way being complete 12 months prior to the completion of construction. | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-900-2 | Right of way Process | Right of Way Plan | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ROW-900-2 | Right of way Process | Right of Way Plan | Right of Way
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-4 | Design Builder Innovation | ADOT does allow ATC during the proposal process. Design-builders will more than likely submit alternative technical concepts for approval and include in their proposal other innovations. A number of opportunities already in the risk profile. Additional opportunities such as pavement may be identified. The assumptions are the total innovations of opportunities will be within the range of 10- 20% of the estimate. The expected value of the opportunities in the current risk profile beyond this opportunity is close to 10% of the contract cost. | Construction
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-4 | Design Builder Innovation | ADOT does allow ATC during the proposal process. Design-builders will more than likely submit alternative technical concepts for approval and include in their proposal other innovations. A number of opportunities already in the risk profile. Additional opportunities such as pavement may be identified. The assumptions are the total innovations of opportunities will be within the range of 10- 20% of the estimate. The expected value of the opportunities in the current risk profile beyond this opportunity is close to 10% of the contract cost. | Construction
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-1 | Eliminating 63rd Avenue bridge | Opportunity to not rebuild the 63rd Avenue Bridge. City is requesting this bridge to be part of this project. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-1 | Eliminating 63rd Avenue bridge | Opportunity to not rebuild the 63rd Avenue Bridge. City is requesting this bridge to be part of this project. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-70-3 | Different Site Conditions | Differing site conditions, type 1 and type 2 soil conditions. Risk is that there will be a type 2 encounter and will become ADOT's | Construction
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-70-3 | Different Site Conditions | Differing site conditions, type 1 and type 2 soil conditions. Risk is that there will be a type 2 encounter and will become ADOT's | Construction
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-2 | Materials Escalation Clauses | Asphalt and diesel fuel have escalation clauses. Asphalt in estimate is about 74,000 tons. Currently ADOT has escalation for asphalt and fuel. | Management and Funding
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-2 | Materials Escalation Clauses | Asphalt and diesel fuel have escalation clauses. Asphalt in estimate is about 74,000 tons. Currently ADOT has escalation for asphalt and fuel. | Management and Funding
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-7 | Opportunity for Developer to Compress Schedule | Base assumes 43 months of construction. Developer proposal may accelerate the schedule to reduce overhead costs. | Construction
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | CNS-900-7 | Opportunity for Developer to Compress Schedule | Base assumes 43 months of construction. Developer proposal may accelerate the schedule to reduce overhead costs. | Construction
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-2 | Geometric Design Change - Vertical Profile | Profile and/or alignment changes. The design is very preliminary. There is an opportunity for further profile optimization to reduce quantities of embankment and borrow. The profile was established, there have been some VE exercises that have made recommendations that have not been implemented into the current base. A profile change could save up to 10% of the borrow and embankment costs, resulting in a cost savings of about $7M. Due to flexibility of being able to use the entire corridor to balance earthwork, developer has a higher likelihood. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-2 | Geometric Design Change - Vertical Profile | Profile and/or alignment changes. The design is very preliminary. There is an opportunity for further profile optimization to reduce quantities of embankment and borrow. The profile was established, there have been some VE exercises that have made recommendations that have not been implemented into the current base. A profile change could save up to 10% of the borrow and embankment costs, resulting in a cost savings of about $7M. Due to flexibility of being able to use the entire corridor to balance earthwork, developer has a higher likelihood. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-10 | Pavement Design Change | Base assumes 13-inch concrete over AC. Opportunity the developer may propose a different roadway section that can reduce costs. This is highly likely since they are responsible for 30 years of maintenance. Current pavement costs (including everything - ramps, etc.) are $101.8M. Developer could have efficiencies of up to 5%. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-10 | Pavement Design Change | Base assumes 13-inch concrete over AC. Opportunity the developer may propose a different roadway section that can reduce costs. This is highly likely since they are responsible for 30 years of maintenance. Current pavement costs (including everything - ramps, etc.) are $101.8M. Developer could have efficiencies of up to 5%. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-3 | Drainage Design Change | The 15% design was a conservative drainage estimate. There is currently $60M in drainage costs. There is $20M in onsite drainage, $40M in offsite drainage. There could be innovation in the offsite system resulting in savings. Could be smaller, deeper ponds with reuse of embankment in other areas. Design is based on 50-year storm design for all areas and may not be required. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-3 | Drainage Design Change | The 15% design was a conservative drainage estimate. There is currently $60M in drainage costs. There is $20M in onsite drainage, $40M in offsite drainage. There could be innovation in the offsite system resulting in savings. Could be smaller, deeper ponds with reuse of embankment in other areas. Design is based on 50-year storm design for all areas and may not be required. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-1 | Optimizing the length of multi-use crossings | There is an opportunity to reduce the length of wildlife/multi-use crossings. This could include revision of structure type. Totao cost in base are around 32M | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-1 | Optimizing the length of multi-use crossings | There is an opportunity to reduce the length of wildlife/multi-use crossings. This could include revision of structure type. Totao cost in base are around 32M | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-50-4 | Stakeholders have requested changes to 51st Avenue Interchange | 51st Avenue to Elliot Road Segment 4 Revisions to the interchange could add scope to the project that could add design time but save construction cost savings. Revisions could remove one structure and revisions to ramps. | Stakeholder
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-50-4 | Stakeholders have requested changes to 51st Avenue Interchange | 51st Avenue to Elliot Road Segment 4 Revisions to the interchange could add scope to the project that could add design time but save construction cost savings. Revisions could remove one structure and revisions to ramps. | Stakeholder
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-50-2 | Reevaluations of sound walls | Current base has height and lengths of sound walls and price per square foot. $36M in estimate currently for sound walls. The process for requirements of sound walls has not been completed so there is uncertainty. Added development could add requirements for sound walls. $20M of the total cost is in the Pecos road area. | Environmental
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-50-2 | Reevaluations of sound walls | Current base has height and lengths of sound walls and price per square foot. $36M in estimate currently for sound walls. The process for requirements of sound walls has not been completed so there is uncertainty. Added development could add requirements for sound walls. $20M of the total cost is in the Pecos road area. | Environmental
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-50-3 | ITS / Advanced Traffic Management | There could be additional ITS costs required, it could be required to open up with all hardware. To fully equip the corridor may cost an additional $25M. Update 9.17.14 - Estimate now includes $25M. This was based on a per mile cost estimated cost. Risk that active traffic management may be needed to the standard FMS. Could cost an additional $250K per mile. | Traffic
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-50-3 | ITS / Advanced Traffic Management | There could be additional ITS costs required, it could be required to open up with all hardware. To fully equip the corridor may cost an additional $25M. Update 9.17.14 - Estimate now includes $25M. This was based on a per mile cost estimated cost. Risk that active traffic management may be needed to the standard FMS. Could cost an additional $250K per mile. | Traffic
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-4 | Opportunity to Reduce Shoulders Width | Base assumes 12 ft. of shoulder width - Standard is 10ft. i.e., 2 % reduction in cross section. (2% of project cost is 36 M). This includes all construction and associated row costs. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | DES-10-4 | Opportunity to Reduce Shoulders Width | Base assumes 12 ft. of shoulder width - Standard is 10ft. i.e., 2 % reduction in cross section. (2% of project cost is 36 M). This includes all construction and associated row costs. | Design
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ENV-60-1 | Unknown environmental mitigation plan and costs | It is unknown if any more mitigation would be added throughout the development of the project. Could be added mitigation for pedestrian or wildlife crossings, added bike paths, plant life, could include injunctive relief costs. Still under requirements to consult with the tribe during design. Risk of revised scope. Currently five crossings identified. Risk is that additional crossings or revisions to these is required. | Environmental
Initial |  | SR 202L South Mountain Freeway Project |  | AZ | ENV-60-1 | Unknown environmental mitigation plan and costs | It is unknown if any more mitigation would be added throughout the development of the project. Could be added mitigation for pedestrian or wildlife crossings, added bike paths, plant life, could include injunctive relief costs. Still under requirements to consult with the tribe during design. Risk of revised scope. Currently five crossings identified. Risk is that additional crossings or revisions to these is required. | Environmental